## Overview
Field | Value
Module | CAPEX_Master
Item_ID | PROCUREMENT_STATUS_001
Description | Status nabavke ključnih komponenti i paketa
Currency | EUR
Total_CAPEX_Midpoint | 58275000
Procurement_Completed_% | 5–10%
Procurement_In_Progress_% | 30–40%
Procurement_Planned_% | 50–60%
Critical_Long_Lead_Items | Production equipment; Testing hall; Heavy cranes; AGV; ERP/MES
Protocol_Link | UNI-MAK Canonical Memory / Procurement Protocol v1

## Categories
Category | Category_Total_EUR | Notes
Material Handling & Logistics | 15445000 | Cranes, AGV, trolleys, forklifts
IT Infrastructure | 1492000 | ERP/MES, servers, network
Construction Packages | 18255000 | Engineering, steel structure, contingency
Production & Testing Equipment | 17000000 | Production lines, testing hall
Utilities & Other | 6308000 | Utilities + renewables

## Subcomponents
Category | Item | Main Suppliers | Estimated Cost EUR | Status | Target Delivery | Notes/Risks
Material Handling & Logistics | Heavy Duty Overhead Cranes | Konecranes; Demag; GH; ABUS | 3400000 | Tendered | Q2 2027 | Critical assembly equipment
Material Handling & Logistics | Secondary Bridge Cranes | Konecranes; Demag | 2520000 | Tendered | Q3 2027 | Integration with crane rails
Material Handling & Logistics | Heavy Transport Trolleys | Enerpac; Hilman | 1280000 | Planned | Q4 2027 | Transformer transport
Material Handling & Logistics | Automated Guided Vehicles | KUKA; Daifuku | 1680000 | Planned | Q2 2028 | MES integration risk
IT Infrastructure | ERP / MES Systems | SAP; Oracle; Siemens Opcenter | 750000 | Tendered | Q2 2028 | Integration with production
IT Infrastructure | Server Infrastructure | Dell; HP; Lenovo | 22500 | Tendered | Q3 2027 | Backend redundancy required
Construction Packages | Projektovanje / Geodezija | Montprojekt; Geoinvest; Arup | 625000 | Completed | Q1 2026 | Engineering phase finished
Construction Packages | Čelična Konstrukcija Hale | ArcelorMittal; Lindab; Montstal | 2800000 | Tendered | Q1 2027 | Steel price volatility
Construction Packages | Contingency Reserve | N/A | 1400000 | Ongoing | Ongoing | Inflation buffer
Production & Testing Equipment | Production Equipment | Hedrich; Tuboly-Astronic | 10000000 | Planned | Q3 2028 | Long lead item
Production & Testing Equipment | Testing Hall Equipment | HAEFELY; Omicron; Megger | 5000000 | Planned | Q4 2028 | HV compliance
Utilities & Other | Utilities Systems | ABB; Schneider; EPCG | 4625000 | Tendered | Q2-Q4 2027 | Grid connection risk
Utilities & Other | Solar PV System | EPCG Solar; EU suppliers | 1000000 | Planned | Q3 2028 | Potential EU grants

## Risks
Risk Category | Description | Mitigation
Supply Chain | EU/China imports; electronics and steel volatility | Multiple suppliers; early tenders
Lead Time | 12–18 months for specialized equipment | Order equipment early
Integration | ERP/MES integration with AGV and production lines | Technical integration planning
Inflation | 5–10% annual equipment inflation | Contingency 10–15%