## README
UNI-MAK CANONICAL MEMORY / BANK-GRADE CAPEX MODEL
Section | Value | Comment
Model status | Working bank-grade model | Canonical baseline set to segment breakdown total of €67.5m.
Workbook purpose | Working bank-grade model | Canonical baseline set to annual phasing implied by segment-by-year memory: €68.3m.
Core assumptions | Construction + funding + DSCR + risk | Supports CAPEX phasing, S-curve monthly cash flow, debt/equity/grant draw schedule, DSCR-ready debt service view, Monte Carlo contingency analytics, and dashboard.
Debt structure | Illustrative | Debt share 55%, Equity 35%, Grants 10%, interest 7.0%, repayment tenor 8 years, first repayment in 2030. Replace with term sheet once available.
CFADS | Illustrative placeholder | 2030-2037 CFADS assumptions are placeholders for DSCR testing and should be replaced with operating model outputs.
Monte Carlo | 500 trials | Deterministic random seeds are embedded for reproducibility. Excel recalc still works on formulas tied to the seed sheet.
Sheet map
Sheet | Use
INPUTS | Project assumptions, annual CAPEX, funding, DSCR, S-curve and Monte Carlo drivers
SEGMENT_CANONICAL | Canonical segment x year memory retained from previous consistency cleanup
YEARLY_CAPEX | Annual phasing and year-over-year profile
S_CURVE | Monthly within-year weights using blended logistic + Gompertz curves
CAPEX_MONTHLY | 48-month cash flow profile and cumulative S-curve
FUNDING_DRAWS | Monthly debt/equity/grant schedule with IDC and annual funding summary
DSCR_SCHEDULE | Construction debt bridge into annual debt service / DSCR view
MONTE_CARLO | Contingency stress test with percentile outputs
DASHBOARD | Management control tower

## INPUTS
MODEL INPUTS / ASSUMPTIONS
Item | Value | Units | Comment
Project | Transformer Plant - Phase Implementation |  | User-provided CAPEX_TIMELINE_001.
Currency | EUR |  | Presentation currency.
Base total CAPEX |  | EUR | Canonical baseline from segment breakdown.
Base contingency |  | EUR | Source: segment breakdown / Contingency total.
CAPEX ex contingency |  | EUR | Derived.
COD / repayment start | 2030 | Year | Illustrative; update when term sheet is fixed.
Year | Annual CAPEX | % of Total | Comment |  | Funding assumption | Value | Units | Comment
2026 |  |  | Canonical annual phasing from segment-by-year cleanup. |  | Debt share | 55% | % | Senior debt share of total CAPEX.
2027 |  |  | Canonical annual phasing from segment-by-year cleanup. |  | Equity share | 35% | % | Sponsor equity share of total CAPEX.
2028 |  |  | Canonical annual phasing from segment-by-year cleanup. |  | Grant share | 10% | % | Grant share of total CAPEX.
2029 |  |  | Canonical annual phasing from segment-by-year cleanup. |  | Funding share check |  | % | Must equal 100.0%.
[5 empty] | Annual debt interest | 7% | % | Construction and operating debt rate.
[5 empty] | Repayment tenor | 8 | Years | Fixed annuity assumption.
[5 empty] | Minimum DSCR | 1.25 | x | Bank covenant test.
Year | Blend α | Logistic k | Logistic x0 | Gompertz b | Gompertz c |  | Ops Year | CFADS | Comment
2026 | 45% | 0.65 | 7 | 0.42 | 7.8 |  | 2030 | 7000000 | Illustrative placeholder; replace with operating model.
2027 | 60% | 0.8 | 6 | 0.55 | 6 |  | 2031 | 8500000 | Illustrative placeholder; replace with operating model.
2028 | 35% | 0.7 | 7 | 0.5 | 7.5 |  | 2032 | 10500000 | Illustrative placeholder; replace with operating model.
2029 | 50% | 0.75 | 6.5 | 0.5 | 7 |  | 2033 | 12000000 | Illustrative placeholder; replace with operating model.
[7 empty] | 2034 | 13500000 | Illustrative placeholder; replace with operating model.
[7 empty] | 2035 | 14500000 | Illustrative placeholder; replace with operating model.
[7 empty] | 2036 | 15000000 | Illustrative placeholder; replace with operating model.
[7 empty] | 2037 | 15000000 | Illustrative placeholder; replace with operating model.
[5 empty] | Monte Carlo input | Value | Units | Comment
[5 empty] | Trials | 500 | count | Deterministic seeds embedded in hidden sheet.
[5 empty] | Delay max months | 6 | months | Permit / contractor delay stress.
[5 empty] | Delay cost / month | 0.35% | % | Applies to civil exposure.
[5 empty] | Materials mean shock | 4% | % | Normal shock mean.
[5 empty] | Materials std dev | 3% | % | Normal shock sigma.
[5 empty] | Lead-time event probability | 30% | % | Equipment procurement event.
[5 empty] | Lead-time event impact | 6% | % | Applies to equipment exposure.
[5 empty] | Commissioning probability | 25% | % | Commissioning event.
[5 empty] | Commissioning impact | 4% | % | Applies to commissioning exposure.
[5 empty] | Civil exposure | 35% | % | Share of CAPEX exposed to civil risk.
[5 empty] | Equipment exposure | 40% | % | Share of CAPEX exposed to equipment risk.
[5 empty] | Commissioning exposure | 10% | % | Share of CAPEX exposed to commissioning risk.
Funding share status
Canonical total check
Note on B13: Source: User-provided CAPEX_TIMELINE_001; normalized to canonical segment breakdown.
Note on G13: Illustrative leverage split. Replace with lender term sheet.
Note on B14: Source: User-provided CAPEX_TIMELINE_001; normalized to canonical segment breakdown.
Note on G14: Illustrative sponsor equity share.
Note on B15: Source: User-provided CAPEX_TIMELINE_001; normalized to canonical segment breakdown.
Note on G15: Illustrative grants share. Adjust for actual eligible CAPEX.
Note on B16: Source: User-provided CAPEX_TIMELINE_001; normalized to canonical segment breakdown.
Note on G17: Illustrative all-in annual debt rate.
Note on I23: Placeholder CFADS for DSCR testing only.

## SEGMENT_CANONICAL
CANONICAL SEGMENT PHASING MEMORY
Segment | 2026 | 2027 | 2028 | 2029 | Total | Comment
Civil works | 1000000 | 14000000 | 2000000 | 1255000 |  | Canonical memory retained from segment-led normalization.
Production equipment | 0 | 0 | 8000000 | 2000000 |  | Canonical memory retained from segment-led normalization.
Testing hall | 0 | 0 | 4000000 | 1000000 |  | Canonical memory retained from segment-led normalization.
Drying systems | 0 | 0 | 1500000 | 500000 |  | Canonical memory retained from segment-led normalization.
Utilities | 0 | 2000000 | 2000000 | 625000 |  | Canonical memory retained from segment-led normalization.
Logistics | 0 | 3000000 | 10000000 | 2445000 |  | Canonical memory retained from segment-led normalization.
IT | 100000 | 200000 | 1500000 | 292000 |  | Canonical memory retained from segment-led normalization.
Engineering | 625000 | 0 | 0 | 0 |  | Canonical memory retained from segment-led normalization.
Project management | 500000 | 500000 | 500000 | 500000 |  | Canonical memory retained from segment-led normalization.
Renewables | 0 | 0 | 1000000 | 0 |  | Canonical memory retained from segment-led normalization.
QA / transport / security | 0 | 0 | 500000 | 1500000 |  | Canonical memory retained from segment-led normalization.
Contingency | 1000000 | 3000000 | 1000000 | 258000 |  | Canonical memory retained from segment-led normalization.
TOTAL

## YEARLY_CAPEX
ANNUAL CAPEX PHASING
Year | Annual CAPEX | % Total | YoY Change | Cumulative CAPEX | Cumulative %
2026
2027
2028
2029

## S_CURVE
BLENDED MONTHLY CAPEX S-CURVE (LOGISTIC + GOMPERTZ)
Month # | 2026 | 2027 | 2028 | 2029
1
2
3
4
5
6
7
8
9
10
11
12
Cumulative | 2026 | 2027 | 2028 | 2029
1
2
3
4
5
6
7
8
9
10
11
12

## CAPEX_MONTHLY
MONTHLY CAPEX CASH FLOW
KPI | Value | Units | Comment
Total CAPEX |  | EUR | Should match canonical total.
Peak monthly draw |  | EUR | Peak cash requirement.
Peak month |  |  | Date of peak draw.
Date | Year | Month # | Annual CAPEX | Weight | Monthly CAPEX | Cumulative CAPEX | Cumulative % | Year-to-date CAPEX
2026-01-01 | 2026 | 1
2026-02-01 | 2026 | 2
2026-03-01 | 2026 | 3
2026-04-01 | 2026 | 4
2026-05-01 | 2026 | 5
2026-06-01 | 2026 | 6
2026-07-01 | 2026 | 7
2026-08-01 | 2026 | 8
2026-09-01 | 2026 | 9
2026-10-01 | 2026 | 10
2026-11-01 | 2026 | 11
2026-12-01 | 2026 | 12
2027-01-01 | 2027 | 1
2027-02-01 | 2027 | 2
2027-03-01 | 2027 | 3
2027-04-01 | 2027 | 4
2027-05-01 | 2027 | 5
2027-06-01 | 2027 | 6
2027-07-01 | 2027 | 7
2027-08-01 | 2027 | 8
2027-09-01 | 2027 | 9
2027-10-01 | 2027 | 10
2027-11-01 | 2027 | 11
2027-12-01 | 2027 | 12
2028-01-01 | 2028 | 1
2028-02-01 | 2028 | 2
2028-03-01 | 2028 | 3
2028-04-01 | 2028 | 4
2028-05-01 | 2028 | 5
2028-06-01 | 2028 | 6
2028-07-01 | 2028 | 7
2028-08-01 | 2028 | 8
2028-09-01 | 2028 | 9
2028-10-01 | 2028 | 10
2028-11-01 | 2028 | 11
2028-12-01 | 2028 | 12
2029-01-01 | 2029 | 1
2029-02-01 | 2029 | 2
2029-03-01 | 2029 | 3
2029-04-01 | 2029 | 4
2029-05-01 | 2029 | 5
2029-06-01 | 2029 | 6
2029-07-01 | 2029 | 7
2029-08-01 | 2029 | 8
2029-09-01 | 2029 | 9
2029-10-01 | 2029 | 10
2029-11-01 | 2029 | 11
2029-12-01 | 2029 | 12

## FUNDING_DRAWS
MONTHLY FUNDING DRAW SCHEDULE
Year | CAPEX | Grant | Equity | Debt | IDC
2026
2027
2028
2029
Date | Direct CAPEX | Grant Draw | Net CAPEX | Equity Draw | Debt Draw | Opening Debt | IDC | Closing Debt | Cum Grants | Cum Equity | Cum Debt
2026-01-01 | [5 empty] | 0
2026-02-01
2026-03-01
2026-04-01
2026-05-01
2026-06-01
2026-07-01
2026-08-01
2026-09-01
2026-10-01
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
2027-04-01
2027-05-01
2027-06-01
2027-07-01
2027-08-01
2027-09-01
2027-10-01
2027-11-01
2027-12-01
2028-01-01
2028-02-01
2028-03-01
2028-04-01
2028-05-01
2028-06-01
2028-07-01
2028-08-01
2028-09-01
2028-10-01
2028-11-01
2028-12-01
2029-01-01
2029-02-01
2029-03-01
2029-04-01
2029-05-01
2029-06-01
2029-07-01
2029-08-01
2029-09-01
2029-10-01
2029-11-01
2029-12-01
TOTAL

## DSCR_SCHEDULE
DSCR-READY DEBT SCHEDULE
Debt metric | Value | Units | Comment
First repayment year |  | Year | Linked.
Repayment tenor |  | Years | Linked.
Annual rate |  | % | Linked.
Minimum DSCR |  | x | Linked.
Opening debt at repayment start |  | EUR | Derived.
Year |  | Debt Draw | IDC | Interest | Debt Service | Principal | Closing Debt | CFADS | DSCR | Covenant | Comment
2026 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | Construction period / debt capitalization.
2027 |  |  |  | 0 | 0 | 0 |  | 0 |  |  | Construction period / debt capitalization.
2028 |  |  |  | 0 | 0 | 0 |  | 0 |  |  | Construction period / debt capitalization.
2029 |  |  |  | 0 | 0 | 0 |  | 0 |  |  | Construction period / debt capitalization.
2030 |  | 0 | 0 | [7 empty] | Operating period / annuity debt service.
2031 |  | 0 | 0 | [7 empty] | Operating period / annuity debt service.
2032 |  | 0 | 0 | [7 empty] | Operating period / annuity debt service.
2033 |  | 0 | 0 | [7 empty] | Operating period / annuity debt service.
2034 |  | 0 | 0 | [7 empty] | Operating period / annuity debt service.
2035 |  | 0 | 0 | [7 empty] | Operating period / annuity debt service.
2036 |  | 0 | 0 | [7 empty] | Operating period / annuity debt service.
2037 |  | 0 | 0 | [7 empty] | Operating period / annuity debt service.

## MC_SEEDS (hidden)
Trial | Delay Months | Materials Shock | Lead Event | Commissioning Event
1 | 3.84 | 0 | 0.06 | 0.04
2 | 4.42 | 0.053755 | 0 | 0.04
3 | 2.53 | 0 | 0.06 | 0
4 | 0.16 | 0.014627 | 0 | 0
5 | 1.32 | 0.04677 | 0 | 0.04
6 | 4.83 | 0.055572 | 0 | 0.04
7 | 5.74 | 0.027347 | 0.06 | 0.04
8 | 5.08 | 0.04789 | 0 | 0
9 | 3.22 | 0.097861 | 0 | 0
10 | 4.98 | 0.049048 | 0 | 0
11 | 4.23 | 0 | 0.06 | 0
12 | 0.48 | 0.018109 | 0.06 | 0
13 | 3.81 | 0.029633 | 0 | 0.04
14 | 1.6 | 0.085818 | 0 | 0
15 | 1.03 | 0.058305 | 0.06 | 0
16 | 5.94 | 0.050754 | 0 | 0
17 | 5.06 | 0.062763 | 0.06 | 0.04
18 | 1.89 | 0.02141 | 0.06 | 0
19 | 5.26 | 0.025521 | 0 | 0
20 | 5.49 | 0.0369 | 0.06 | 0.04
21 | 3.37 | 0.020953 | 0 | 0
22 | 2.4 | 0.016765 | 0 | 0
23 | 0.55 | 0 | 0.06 | 0
24 | 4.75 | 0.034109 | 0.06 | 0
25 | 5.98 | 0.042191 | 0 | 0
26 | 0.07 | 0.05755 | 0 | 0
27 | 1.6 | 0.050831 | 0.06 | 0
28 | 2.72 | 0.090491 | 0 | 0
29 | 3 | 0.012385 | 0 | 0
30 | 1.79 | 0.05067 | 0 | 0.04
31 | 4.58 | 0.042966 | 0 | 0
32 | 0 | 0.026317 | 0.06 | 0
33 | 5.27 | 0.068823 | 0 | 0.04
34 | 5.27 | 0.088479 | 0.06 | 0
35 | 0.42 | 0.061247 | 0 | 0.04
36 | 2.85 | 0.043755 | 0.06 | 0
37 | 2.54 | 0.015994 | 0 | 0
38 | 1.21 | 0.02527 | 0 | 0
39 | 2.63 | 0.041322 | 0.06 | 0.04
40 | 2.03 | 0.046696 | 0.06 | 0.04
41 | 0.43 | 0.050043 | 0.06 | 0
42 | 5.16 | 0 | 0.06 | 0
43 | 1.29 | 0.0065341 | 0 | 0
44 | 2.84 | 0.063637 | 0 | 0.04
45 | 0.58 | 0.034789 | 0 | 0
46 | 4.37 | 0.053477 | 0 | 0.04
47 | 2.42 | 0.027569 | 0 | 0.04
48 | 1.14 | 0.036125 | 0 | 0
49 | 1.5 | 0.082822 | 0 | 0
50 | 3.3 | 0 | 0 | 0
51 | 5.81 | 0.083478 | 0 | 0.04
52 | 2.91 | 0.016195 | 0 | 0.04
53 | 2.27 | 0.10535 | 0.06 | 0
54 | 2.73 | 0.034174 | 0 | 0
55 | 3.33 | 0.057344 | 0.06 | 0
56 | 5.81 | 0.045994 | 0 | 0
57 | 0.34 | 0.046378 | 0 | 0
58 | 0.94 | 0.092794 | 0.06 | 0.04
59 | 3.57 | 0.053631 | 0.06 | 0.04
60 | 5.34 | 0.019407 | 0 | 0
61 | 2.52 | 0.046339 | 0 | 0
62 | 1.23 | 0.057147 | 0.06 | 0
63 | 4.03 | 0.024268 | 0 | 0
64 | 0.44 | 0.036857 | 0 | 0
65 | 0.44 | 0.016134 | 0.06 | 0
66 | 5.29 | 0.07514 | 0 | 0.04
67 | 5 | 0.056038 | 0 | 0
68 | 3.92 | 0 | 0 | 0
69 | 3.98 | 0.086376 | 0.06 | 0.04
70 | 0.64 | 0.044014 | 0.06 | 0
71 | 4.31 | 0.015135 | 0 | 0
72 | 2.93 | 0.079377 | 0 | 0.04
73 | 2.54 | 0.022218 | 0.06 | 0
74 | 3.82 | 0.02088 | 0 | 0
75 | 2.57 | 0 | 0.06 | 0
76 | 5.42 | 0.043436 | 0 | 0
77 | 0.89 | 0.0058435 | 0 | 0
78 | 4.78 | 0.072504 | 0 | 0.04
79 | 1.5 | 0.0020262 | 0 | 0
80 | 2.44 | 0.049217 | 0.06 | 0
81 | 5.19 | 0.099431 | 0 | 0
82 | 0.15 | 0.058984 | 0 | 0
83 | 4.81 | 0.072963 | 0 | 0
84 | 4.72 | 0.0028984 | 0 | 0
85 | 1.33 | 0.067073 | 0 | 0
86 | 4.77 | 0.017596 | 0.06 | 0.04
87 | 1.97 | 0.073003 | 0 | 0
88 | 3.85 | 0.032375 | 0 | 0
89 | 5.64 | 0.004042 | 0 | 0.04
90 | 5.78 | 0.021203 | 0.06 | 0
91 | 4.37 | 0.025436 | 0 | 0
92 | 2.31 | 0.045795 | 0.06 | 0
93 | 0.01 | 0.083308 | 0 | 0
94 | 4.45 | 0.053249 | 0 | 0.04
95 | 3.99 | 0.026819 | 0 | 0
96 | 4.32 | 0.024296 | 0 | 0
97 | 2.41 | 0.023892 | 0.06 | 0
98 | 5.64 | 0.053806 | 0 | 0
99 | 1.81 | 0.043614 | 0.06 | 0
100 | 2.58 | 0.046056 | 0 | 0
101 | 2.65 | 0.016191 | 0 | 0
102 | 4.78 | 0.011338 | 0.06 | 0
103 | 3.8 | 0.027231 | 0 | 0
104 | 4.04 | 0.017302 | 0.06 | 0.04
105 | 1.47 | 0.038129 | 0 | 0.04
106 | 2.49 | 0.049937 | 0.06 | 0
107 | 2.97 | 0.019194 | 0 | 0.04
108 | 4.51 | 0.06217 | 0.06 | 0
109 | 1.06 | 0.091827 | 0 | 0.04
110 | 1.5 | 0.07088 | 0 | 0
111 | 4.01 | 0.10761 | 0 | 0
112 | 5.35 | 0.048587 | 0 | 0
113 | 4.98 | 0.043609 | 0 | 0
114 | 2.85 | 0.020625 | 0.06 | 0
115 | 4.59 | 0.041602 | 0 | 0
116 | 0.46 | 0.023023 | 0.06 | 0
117 | 3.24 | 0.0073704 | 0.06 | 0
118 | 4.24 | 0 | 0 | 0
119 | 2.49 | 0.015476 | 0 | 0
120 | 3.5 | 0.055347 | 0 | 0
121 | 2.28 | 0 | 0 | 0
122 | 5.12 | 0.090372 | 0 | 0
123 | 3.28 | 0.047853 | 0.06 | 0.04
124 | 2.62 | 0 | 0 | 0
125 | 2.43 | 0.010782 | 0 | 0.04
126 | 3.73 | 0 | 0 | 0
127 | 0.16 | 0.050975 | 0.06 | 0
128 | 0.3 | 0.030765 | 0.06 | 0
129 | 4.57 | 0.030767 | 0 | 0
130 | 1.51 | 0 | 0.06 | 0
131 | 6 | 0.028437 | 0 | 0
132 | 3.91 | 0.060636 | 0 | 0.04
133 | 0.12 | 0.0092119 | 0.06 | 0
134 | 3.38 | 0.016627 | 0 | 0
135 | 1.01 | 0.048165 | 0 | 0.04
136 | 4.92 | 0.094249 | 0.06 | 0.04
137 | 1.87 | 0.053809 | 0 | 0
138 | 4.29 | 0 | 0 | 0
139 | 0.61 | 0.062411 | 0 | 0
140 | 0.73 | 0.10422 | 0 | 0
141 | 2.57 | 0.03009 | 0 | 0
142 | 5.1 | 0.067729 | 0.06 | 0
143 | 3.81 | 0.068472 | 0 | 0
144 | 4.4 | 0.094542 | 0.06 | 0
145 | 3.23 | 0.038759 | 0 | 0
146 | 1.61 | 0.071314 | 0 | 0.04
147 | 5.29 | 0.019182 | 0 | 0
148 | 2.27 | 0 | 0 | 0.04
149 | 1.27 | 0.065017 | 0 | 0
150 | 4.21 | 0.022181 | 0.06 | 0
151 | 0.51 | 0.057492 | 0 | 0
152 | 4.14 | 0.051228 | 0 | 0
153 | 0.56 | 0.016996 | 0 | 0
154 | 3.49 | 0.037988 | 0 | 0
155 | 4.48 | 0.026868 | 0 | 0
156 | 1.51 | 0.0048486 | 0.06 | 0.04
157 | 3.22 | 0.061401 | 0.06 | 0.04
158 | 2.91 | 0.057896 | 0 | 0
159 | 1.7 | 0.0016432 | 0.06 | 0.04
160 | 1.08 | 0 | 0 | 0
161 | 5.85 | 0.044025 | 0 | 0.04
162 | 5.21 | 0.039314 | 0 | 0
163 | 2.82 | 0.035507 | 0.06 | 0.04
164 | 5.65 | 0.038324 | 0 | 0
165 | 0.44 | 0.049912 | 0.06 | 0.04
166 | 3.38 | 0.024598 | 0 | 0.04
167 | 4.59 | 0.048092 | 0 | 0.04
168 | 3.14 | 0.036269 | 0 | 0
169 | 5.94 | 0.02473 | 0 | 0
170 | 4.44 | 0.088658 | 0.06 | 0.04
171 | 3.96 | 0.0098012 | 0.06 | 0.04
172 | 0.02 | 0.036268 | 0 | 0
173 | 1.39 | 0.056335 | 0 | 0
174 | 4.12 | 0.082956 | 0 | 0
175 | 3.97 | 0.08511 | 0 | 0
176 | 3.89 | 0.079931 | 0 | 0.04
177 | 1 | 0.024921 | 0 | 0
178 | 1.73 | 0.0053952 | 0 | 0
179 | 5.66 | 0.040036 | 0 | 0.04
180 | 0.24 | 0.034864 | 0 | 0
181 | 0.55 | 0.093199 | 0 | 0
182 | 5.7 | 0.14003 | 0 | 0
183 | 0.24 | 0.060831 | 0 | 0
184 | 5.5 | 0.012709 | 0 | 0
185 | 2.95 | 5.7038e-06 | 0 | 0
186 | 4.02 | 0.072106 | 0 | 0
187 | 1.73 | 0.087998 | 0 | 0
188 | 2.73 | 0.025507 | 0 | 0
189 | 2.43 | 0.041098 | 0 | 0
190 | 3.26 | 0.033424 | 0.06 | 0
191 | 4.54 | 0.049592 | 0 | 0.04
192 | 3.3 | 0.08376 | 0 | 0
193 | 0.73 | 0.097876 | 0 | 0.04
194 | 0.95 | 0.043833 | 0 | 0.04
195 | 5.95 | 0.080771 | 0 | 0.04
196 | 4.99 | 0.039878 | 0 | 0
197 | 1.64 | 0.06919 | 0 | 0.04
198 | 3.31 | 0.031118 | 0 | 0
199 | 5.28 | 0.072958 | 0.06 | 0
200 | 2.49 | 0.085246 | 0 | 0
201 | 1.7 | 0.024143 | 0 | 0
202 | 2.94 | 0.0087257 | 0 | 0
203 | 3.31 | 0.043272 | 0 | 0
204 | 1.13 | 0.055517 | 0 | 0.04
205 | 4.65 | 0 | 0 | 0
206 | 4.87 | 0.031313 | 0 | 0
207 | 5.88 | 0.039649 | 0.06 | 0
208 | 3.54 | 0.073749 | 0 | 0
209 | 3.16 | 0.036755 | 0 | 0
210 | 3.93 | 0.0094628 | 0 | 0
211 | 2.03 | 0.055106 | 0 | 0
212 | 5.11 | 0.072321 | 0 | 0
213 | 4.31 | 0.061131 | 0 | 0.04
214 | 0.41 | 0.050048 | 0 | 0
215 | 4.48 | 0.035012 | 0.06 | 0
216 | 5.24 | 0.035751 | 0 | 0
217 | 0.28 | 0.064838 | 0.06 | 0
218 | 0.87 | 0.042346 | 0 | 0
219 | 1.02 | 0 | 0 | 0
220 | 1.44 | 0.080752 | 0.06 | 0
221 | 1.52 | 0.020265 | 0.06 | 0
222 | 5.41 | 0.053831 | 0.06 | 0
223 | 2.07 | 0.046639 | 0 | 0
224 | 1.5 | 0.070495 | 0.06 | 0
225 | 2.9 | 0.01854 | 0 | 0
226 | 5.96 | 0.023855 | 0 | 0
227 | 1.65 | 0.044981 | 0 | 0
228 | 0.29 | 0.048099 | 0 | 0
229 | 1.72 | 0.065127 | 0 | 0
230 | 3.82 | 0.049235 | 0 | 0
231 | 3.96 | 0.069629 | 0 | 0
232 | 3.88 | 0.025034 | 0 | 0
233 | 4.39 | 0 | 0.06 | 0
234 | 1.05 | 0.0065128 | 0 | 0
235 | 3.19 | 0.080876 | 0 | 0
236 | 4.95 | 0.038635 | 0 | 0
237 | 2.03 | 0.0040155 | 0 | 0.04
238 | 5.8 | 0.072429 | 0 | 0
239 | 5.8 | 0.065744 | 0 | 0
240 | 0.08 | 0.042754 | 0 | 0
241 | 4.03 | 0.046407 | 0 | 0
242 | 0.65 | 0.01821 | 0.06 | 0
243 | 3.37 | 0.081216 | 0.06 | 0.04
244 | 4.94 | 0.08011 | 0 | 0
245 | 0.84 | 0.088289 | 0 | 0
246 | 0.58 | 0.076362 | 0.06 | 0
247 | 4.02 | 0.059592 | 0 | 0
248 | 4.45 | 0.0094832 | 0 | 0.04
249 | 2.94 | 0.033028 | 0 | 0.04
250 | 2.22 | 0.035728 | 0 | 0
251 | 0.6 | 0.054509 | 0 | 0
252 | 2.15 | 0.032255 | 0.06 | 0.04
253 | 5.09 | 0.036587 | 0 | 0
254 | 3.58 | 0 | 0 | 0.04
255 | 0.76 | 0.044878 | 0.06 | 0
256 | 1.24 | 0.016422 | 0 | 0
257 | 0.89 | 0.078537 | 0.06 | 0
258 | 0.87 | 0.0062072 | 0.06 | 0.04
259 | 3.97 | 0 | 0.06 | 0
260 | 1.43 | 0.026285 | 0.06 | 0.04
261 | 4.45 | 0.041963 | 0 | 0
262 | 4.67 | 0.040996 | 0.06 | 0
263 | 5.67 | 0 | 0 | 0
264 | 3.13 | 0.036839 | 0 | 0.04
265 | 2.87 | 0.032525 | 0 | 0
266 | 5.46 | 0 | 0.06 | 0
267 | 0.39 | 0.022069 | 0 | 0
268 | 1.95 | 0.11653 | 0 | 0
269 | 3.63 | 0.0014126 | 0 | 0
270 | 3.91 | 0.062063 | 0 | 0.04
271 | 2.71 | 0.017685 | 0 | 0
272 | 2.5 | 0.00069786 | 0 | 0
273 | 2.25 | 0.0092446 | 0 | 0.04
274 | 4.99 | 0.0003663 | 0.06 | 0
275 | 4.87 | 0.044253 | 0 | 0
276 | 1.98 | 0.0050829 | 0 | 0
277 | 4.5 | 0.073523 | 0 | 0
278 | 3.6 | 0.028574 | 0 | 0.04
279 | 3.94 | 0.017262 | 0.06 | 0
280 | 2.21 | 0.061441 | 0 | 0
281 | 5.07 | 0.098568 | 0 | 0
282 | 3.86 | 0 | 0 | 0
283 | 1.6 | 0.012587 | 0 | 0
284 | 2.04 | 0 | 0 | 0
285 | 2.4 | 0.007842 | 0 | 0.04
286 | 4.48 | 0.016338 | 0 | 0
287 | 2.22 | 0.057628 | 0 | 0
288 | 0.51 | 0 | 0.06 | 0
289 | 4.04 | 0.021806 | 0 | 0
290 | 2.65 | 0.021902 | 0 | 0.04
291 | 2.58 | 0.022803 | 0 | 0
292 | 4 | 0 | 0 | 0
293 | 0.05 | 0.02439 | 0.06 | 0.04
294 | 1.53 | 0.026647 | 0.06 | 0
295 | 1.05 | 0.030852 | 0 | 0
296 | 5 | 0.065919 | 0.06 | 0
297 | 0.25 | 0 | 0 | 0
298 | 3.45 | 0.045551 | 0 | 0
299 | 0.69 | 0 | 0 | 0
300 | 3.71 | 0.068866 | 0 | 0.04
301 | 5.07 | 0.01913 | 0 | 0
302 | 2.37 | 0.025148 | 0 | 0
303 | 1.01 | 0.040788 | 0.06 | 0
304 | 5.44 | 0.02839 | 0 | 0
305 | 4.89 | 0.018449 | 0.06 | 0.04
306 | 3.61 | 0.06121 | 0 | 0.04
307 | 4.64 | 0.039558 | 0 | 0
308 | 2.69 | 0.083007 | 0 | 0
309 | 3.75 | 0.072988 | 0 | 0.04
310 | 0.41 | 0.035639 | 0 | 0
311 | 0.34 | 0.040552 | 0 | 0
312 | 0.34 | 0.068827 | 0.06 | 0
313 | 5.13 | 0.048772 | 0 | 0
314 | 3.33 | 0.064382 | 0 | 0
315 | 4.86 | 0.051709 | 0 | 0
316 | 0.91 | 0 | 0.06 | 0
317 | 2.06 | 0.056981 | 0 | 0.04
318 | 1.49 | 0.0353 | 0 | 0
319 | 0.95 | 0.030271 | 0.06 | 0
320 | 2.03 | 0.047436 | 0 | 0
321 | 0.4 | 0.00059477 | 0 | 0
322 | 4.34 | 0.052093 | 0 | 0
323 | 2 | 0.046267 | 0.06 | 0
324 | 5.81 | 0.055601 | 0 | 0
325 | 5.63 | 0.025089 | 0 | 0
326 | 4.88 | 0.053207 | 0 | 0
327 | 4.11 | 0.041986 | 0 | 0
328 | 2.17 | 0.029454 | 0.06 | 0.04
329 | 5.69 | 0.038967 | 0.06 | 0.04
330 | 0.46 | 0.070385 | 0.06 | 0
331 | 5.01 | 0.075808 | 0.06 | 0
332 | 4.6 | 0.0063566 | 0 | 0.04
333 | 4.99 | 0.062274 | 0 | 0.04
334 | 2.63 | 0.03324 | 0 | 0.04
335 | 2.67 | 0.022952 | 0 | 0
336 | 3.2 | 0.025079 | 0 | 0
337 | 5.01 | 0.029873 | 0 | 0
338 | 2.77 | 0.022672 | 0 | 0
339 | 5.8 | 0.067107 | 0 | 0.04
340 | 1.5 | 0.050848 | 0 | 0
341 | 0.62 | 0.070569 | 0 | 0
342 | 4.58 | 0.021868 | 0 | 0.04
343 | 2.62 | 0.088331 | 0.06 | 0
344 | 2.1 | 0 | 0.06 | 0
345 | 1.41 | 0.11633 | 0 | 0.04
346 | 5.58 | 0.069732 | 0 | 0
347 | 0.83 | 0.023124 | 0 | 0
348 | 0.83 | 0.056212 | 0 | 0.04
349 | 0.48 | 0.020321 | 0 | 0
350 | 4.36 | 0.04209 | 0.06 | 0
351 | 1.81 | 0 | 0 | 0
352 | 2.74 | 0.0033406 | 0 | 0
353 | 0.1 | 0.041157 | 0.06 | 0.04
354 | 2.58 | 0.048756 | 0.06 | 0
355 | 3.99 | 0 | 0 | 0.04
356 | 3.16 | 0.040551 | 0 | 0
357 | 2.34 | 0.037752 | 0 | 0
358 | 1.52 | 0 | 0 | 0
359 | 4.4 | 0.049817 | 0 | 0
360 | 2 | 0 | 0 | 0
361 | 1.05 | 0.063079 | 0 | 0
362 | 3.79 | 0.066503 | 0.06 | 0
363 | 2.75 | 0.023699 | 0.06 | 0.04
364 | 0.25 | 0.085041 | 0 | 0
365 | 3.26 | 0.020077 | 0 | 0.04
366 | 2.14 | 0.063251 | 0 | 0
367 | 0.75 | 0.029887 | 0 | 0
368 | 5.37 | 0.031358 | 0 | 0
369 | 2.99 | 0.08304 | 0 | 0
370 | 4.36 | 0 | 0 | 0
371 | 3.27 | 0.026071 | 0.06 | 0
372 | 1.84 | 0.047804 | 0 | 0
373 | 2.11 | 0 | 0 | 0
374 | 5.99 | 0.022027 | 0 | 0
375 | 0.45 | 0.050555 | 0 | 0
376 | 4.08 | 0.090176 | 0.06 | 0
377 | 4.69 | 0 | 0.06 | 0
378 | 2.2 | 0.03106 | 0 | 0
379 | 4.07 | 0.089007 | 0 | 0
380 | 3.44 | 0.042217 | 0 | 0
381 | 1.5 | 0.0037483 | 0 | 0
382 | 2.32 | 0.044656 | 0.06 | 0
383 | 2.68 | 0.12053 | 0.06 | 0
384 | 2.95 | 0.0051429 | 0 | 0
385 | 5.39 | 0.035859 | 0.06 | 0
386 | 5.07 | 0.025934 | 0 | 0.04
387 | 3.25 | 0.077009 | 0 | 0
388 | 5.56 | 0.05057 | 0 | 0
389 | 0.73 | 0.014856 | 0.06 | 0
390 | 0.16 | 0.044075 | 0 | 0
391 | 3.31 | 0.048532 | 0.06 | 0
392 | 6 | 0.057385 | 0 | 0
393 | 4.94 | 0 | 0 | 0
394 | 2.7 | 0.05404 | 0 | 0
395 | 4.68 | 0.050737 | 0.06 | 0
396 | 2.6 | 0.080355 | 0.06 | 0.04
397 | 0.92 | 0.010735 | 0 | 0
398 | 2.08 | 0.086872 | 0 | 0
399 | 1.5 | 0.050358 | 0 | 0.04
400 | 1.82 | 0.04252 | 0 | 0.04
401 | 5.65 | 0.0094417 | 0 | 0
402 | 3.63 | 0.070147 | 0 | 0
403 | 0.17 | 0 | 0 | 0
404 | 3.91 | 0.061866 | 0 | 0
405 | 2.99 | 0.049731 | 0.06 | 0
406 | 2.9 | 0.065755 | 0 | 0
407 | 0.44 | 0 | 0 | 0
408 | 1.22 | 0.048119 | 0 | 0
409 | 4.41 | 0.072515 | 0 | 0.04
410 | 2.22 | 0.044655 | 0 | 0
411 | 1.6 | 0.019568 | 0.06 | 0
412 | 2.3 | 0.048801 | 0.06 | 0
413 | 0.96 | 0.02659 | 0 | 0
414 | 4.58 | 0.03987 | 0 | 0
415 | 1.85 | 0 | 0 | 0
416 | 5.8 | 0.016339 | 0 | 0.04
417 | 2.97 | 0.075603 | 0 | 0
418 | 3.22 | 0.070731 | 0 | 0
419 | 4.37 | 0.061563 | 0 | 0
420 | 3.42 | 0.014174 | 0 | 0.04
421 | 3.03 | 0.061616 | 0.06 | 0
422 | 4.08 | 0.0045715 | 0 | 0
423 | 4.77 | 0.027551 | 0 | 0
424 | 1.19 | 0.040686 | 0 | 0.04
425 | 0.82 | 0.027054 | 0 | 0
426 | 3.64 | 0.041166 | 0 | 0
427 | 0.98 | 0.1105 | 0 | 0
428 | 2.02 | 0.068423 | 0 | 0
429 | 1.8 | 0.066978 | 0 | 0
430 | 5.88 | 0.046341 | 0 | 0
431 | 4.13 | 0 | 0 | 0
432 | 4.7 | 0.062779 | 0 | 0
433 | 3.5 | 0.011436 | 0 | 0
434 | 5.05 | 0.0086194 | 0 | 0.04
435 | 5.69 | 0.0031875 | 0.06 | 0
436 | 0.91 | 0.054918 | 0 | 0
437 | 5.52 | 0.074194 | 0 | 0.04
438 | 0.83 | 0.01553 | 0 | 0
439 | 3.15 | 0.025443 | 0.06 | 0
440 | 2.05 | 0.028787 | 0 | 0
441 | 3.86 | 0.055158 | 0 | 0.04
442 | 1.48 | 0.044384 | 0.06 | 0
443 | 1.79 | 0.023311 | 0.06 | 0
444 | 1.9 | 0.028343 | 0 | 0
445 | 1.64 | 0.0050299 | 0 | 0
446 | 5.88 | 0.067276 | 0 | 0
447 | 1.74 | 0.02319 | 0 | 0
448 | 2.65 | 0.02037 | 0 | 0.04
449 | 3.23 | 0.084961 | 0 | 0.04
450 | 3.69 | 0.046582 | 0.06 | 0
451 | 3.19 | 0.050589 | 0.06 | 0
452 | 4.3 | 0.0016464 | 0 | 0.04
453 | 3.3 | 0.084074 | 0 | 0
454 | 5.27 | 0.038303 | 0.06 | 0
455 | 1.93 | 0.051228 | 0 | 0.04
456 | 3.44 | 0.042647 | 0 | 0
457 | 5.48 | 0.01197 | 0 | 0.04
458 | 5.52 | 0.12301 | 0 | 0
459 | 5.62 | 0.093279 | 0 | 0
460 | 0.06 | 0.045136 | 0.06 | 0
461 | 1.71 | 0.10881 | 0 | 0
462 | 5.63 | 0.07123 | 0 | 0.04
463 | 0.68 | 0.010472 | 0 | 0
464 | 1.12 | 0.058989 | 0 | 0
465 | 4.54 | 0.01202 | 0 | 0
466 | 4.96 | 0.041149 | 0.06 | 0
467 | 1.11 | 0.0076728 | 0 | 0.04
468 | 1.56 | 0.018376 | 0 | 0
469 | 1.81 | 0.057743 | 0.06 | 0
470 | 4.16 | 0 | 0.06 | 0
471 | 2.43 | 0.04019 | 0 | 0
472 | 1.87 | 0.0043599 | 0 | 0
473 | 3.69 | 0.016746 | 0.06 | 0.04
474 | 4.49 | 0.048047 | 0 | 0
475 | 2.82 | 0.042825 | 0 | 0.04
476 | 1.48 | 0.060684 | 0 | 0.04
477 | 2.68 | 0.056058 | 0.06 | 0
478 | 0.37 | 0.043592 | 0 | 0
479 | 0.9 | 0.026646 | 0 | 0.04
480 | 1.23 | 0.046299 | 0.06 | 0
481 | 4.85 | 0.03649 | 0 | 0
482 | 0.35 | 0.037167 | 0 | 0
483 | 2.38 | 0.067058 | 0 | 0
484 | 0.27 | 0.027996 | 0.06 | 0
485 | 5.61 | 0 | 0 | 0.04
486 | 2.45 | 0.062064 | 0 | 0
487 | 3.88 | 0.033971 | 0 | 0
488 | 5.22 | 0.079633 | 0 | 0
489 | 3.97 | 0.04296 | 0 | 0
490 | 1.07 | 0.042806 | 0 | 0
491 | 1.34 | 0 | 0.06 | 0
492 | 4.04 | 0.043349 | 0 | 0
493 | 1.49 | 0.028129 | 0.06 | 0
494 | 4.35 | 0.0036539 | 0 | 0
495 | 4.6 | 0.075819 | 0.06 | 0.04
496 | 0.61 | 0 | 0 | 0
497 | 0.29 | 0.05935 | 0 | 0.04
498 | 1.3 | 0.072917 | 0.06 | 0
499 | 1.74 | 0.066983 | 0 | 0
500 | 3.59 | 0.053407 | 0 | 0

## MONTE_CARLO
MONTE CARLO CONTINGENCY SIMULATOR
Metric | Value | Units | Comment
Base total CAPEX |  | EUR | Canonical total.
Base contingency reserve |  | EUR | Embedded in baseline.
Expected additional overrun |  | EUR | Mean overrun above baseline.
P50 total CAPEX |  | EUR | Median simulated total.
P75 total CAPEX |  | EUR | Upside stress.
P90 total CAPEX |  | EUR | Conservative stress.
Probability reserve exhausted |  | % | Residual funding gap > 0.
Trial | Delay Months | Materials Shock | Lead Event | Commissioning Event | Overrun % | Total CAPEX | Additional Overrun | Residual Funding Gap | Bin | Count
0%
2%
4%
6%
8%
10%
12%

## DASHBOARD
CAPEX CONTROL TOWER DASHBOARD
Base CAPEX | Peak monthly draw | Debt facility | Equity commitment
Grants | COD debt balance | Minimum DSCR | P90 CAPEX
Reserve exhaustion prob.
This dashboard is formula-linked to the canonical memory sheets. Debt/Equity/Grant, S-curve timing and DSCR placeholders can be adjusted centrally in INPUTS.