## Executive Summary
ARS METAL INDUSTRIES – Nova fabrika Podgorica
Executive Summary – CAPEX & Ključni parametri
Ukupni CAPEX (sa contingency) |  |  | Datum ažuriranja
Verzija | 4.0 – Bank Ready
KPI | Vrijednost | Jedinica | % od ukupnog CAPEX | Low | High | Komentar
Ukupni CAPEX |  | € | 100%
Machine Park |  | €
Hala & građevina |  | €
Contingency |  | €
Soft Costs |  | €
Working Capital |  | €
Kategorija | Iznos (€) | % ukupno
Građevina & hala
Machine Park
Soft Costs
Contingency
Ukupno |  | 100%
Godina/Faza | % CAPEX-a | Iznos (€) | Ključne aktivnosti
2026 | 0.25 |  | Zemljište, dozvole, projektovanje, početak građevine
2027 | 0.55 |  | Glavna građevina, većina mašina, MEP
2028 | 0.2 |  | Završetak, instalacija, commissioning
Rizik | Vjerovatnoća | Utjecaj (€) | Mitigacija
Deprecijacija TRY (+20%) | Srednja |  | 80% hedžovano forward ugovorom
Kašnjenje dozvola | Visoka | 400000 | Već započeta procedura
Viši građevinski troškovi | Srednja | 500000 | Contingency 15% na civil
Veći WC potreban | Srednja | 400000 | Revolving kredit linija

## Depreciation Schedule
PLAN AMORTIZACIJE – DEPRECIATION SCHEDULE
Početak amortizacije: Q3 2028 (mid-year 50%)
Poreske stope (PDPL CG 2026):
I grupa (hala): 2.5% straight-line
II grupa (opšta oprema): 10% degresivno
III grupa (laseri, robot): 15% degresivno
IV grupa (viljuškari, kranovi, generator): 20% degresivno
Računovodstvena amortizacija: straight-line (5–10 godina oprema)
Red | Mašina / Linija | Osnovica (€) | Poreska grupa | Stopa % | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038
1 | UNI-MAK linija | 900000 | II | 0.1
2 | SLS MECANO robot | 80000 | III | 0.15
3 | Abkant + Punta + Giyotin | 342490 | II | 0.1
4 | NKN Laseri | 965000 | III | 0.15
5 | Vinčevi | 785000 | IV | 0.2
6 | GENPOWER generator | 72085 | IV | 0.2
7 | ASTOR pano | 53862 | II | 0.1
8 | Ostale mašine | 747350 | II/III/IV | 0.12
9 | Građevina & hala | 6500000 | I | 0.025
Ukupno amortizacija po godinama
Napomena: Poreska amortizacija smanjuje oporezivu dobit (PDPL). Razlika između poreske i računovodstvene stvara odložene poreze (IAS 12).

## Funding Sources & Uses
ARS METAL INDUSTRIES – FUNDING SOURCES & USES
Ukupni potrebni iznos (CAPEX + WC + finansijski troškovi) | 15887500
IZVORI SREDSTAVA (Sources) | Iznos (€) | % ukupno | NAMENE SREDSTAVA (Uses) | Iznos (€) | % ukupno
Sopstveni kapital / Equity | 3500000 |  | CAPEX bez contingency | 12500000
Grant / Bespovratna sredstva | 1875000 |  | Contingency / Rezerva | 1187500
Investicioni kredit | 8000000 |  | Početni obrtni kapital (WC) | 2200000
Odloženo plaćanje dobavljača | 1200000 |  | Početni finansijski troškovi | 200000
Revolving WC linija | 1312500 |  | Rezerva za kamate tokom grace | 100000
Ukupno IZVORI |  |  | Ukupno NAMENE
Balans (Sources – Uses)
Balans → Sources = Uses (0 razlike → model konzistentan)
Grant cilj 15% (Fond za inovacije / IPA III) – aplikacija u toku
Kredit očekivana kamata 5,2–6,5%, grace 12–18 mjeseci
Equity 22% – može se povećati na 25–30%
WC linija: revolving kredit kod NLB/Addiko/IRF

## ASSUMPTIONS MASTER INPUT
ARS Metal Industries DOO Version 1.0 Date: 25.02.2026 |  | ASSUMPTIONS / MASTER INPUT
[7 empty] | VAT_RATE | DEBT_INT_RATE | 6.5%
Br | KEY | Opis | Base vrijednost | Jedinica | Komentar / Izvor | Status |  | TENOR_MONTHS | 120
[8 empty] | GRACE_MONTHS | 36
1. MACRO & TAX ASSUMPTIONS
MT1 | FX_EUR_TRY | Kurs EUR/TRY (uvoz mašina iz Turske) | 5170% | TRY | ECB/TCMB 24–25.02.2026 | Soft | Najveći valutni rizik (~80 % Machine Park). Hedžuj 80 % u EUR!
MT2 | VAT_STD | Standardna stopa PDV-a | 2100% | % | Zakon o PDV CG | Hard | Skriveni trošak na OPEX – jede EBITDA 2–3 % godišnje
MT3 | VAT_INV | PDV na investicije > 0.5 mil € | 0% | % | Član 25 Zakona o PDV | Hard | Najveći besplatni keš od države (~2.5–2.8 mil € uštede)
MT4 | CIT_RATE | Porez na dobit (efektivna) | 9–15 | % | Zakon o porezu na dobit CG | Hard | Progresivno + tax shield ~0.9–1.1 mil €/god
MT5 | WHT_DIV | Porez po odbitku na dividendu | 1500% | % | Poreski propisi CG | Hard | Reinvestiraj profit prve 3–4 godine + DTU
MT6 | INF_CONSTRUCTION | Inflacija građevinskih troškova | 350% | % | CBCG / tržište 2026 | Soft | Contingency 9.5 % obavezan
MT7 | INF_OPEX | Inflacija operativnih troškova | 250% | % | CBCG / IMF / MONSTAT | Soft | Price pass-through klauzule obavezne
MT8 | DISCOUNT_RATE | Socio-ekonomska diskontna stopa | 800% | % | JASPERS / IPA III | Hard | Samo za grantove i socio-analizu
MT9 | WACC | Weighted Average Cost of Capital | 950% | % | Izračunato | Hard | Project IRR 16.5 % > WACC → NPV pozitivan
MT10 | MODEL_CCY | Model valuta | EUR | text | Sva izvještavanja u EUR | Hard | Eliminira valutni rizik
2. TIMELINE / KEY DATES
TL1 | FINANCIAL_CLOSE | Financial Close | 30.06.2026 | Datum | Nakon odobrenja kredita/granta | Hard | Početak drawdown-a
TL2 | CONSTRUCTION_START | Početak radova | 01.07.2026 | Datum | Odmah nakon dozvola | Hard | Kašnjenje 6 m → IRR -2–3 pp
TL3 | HALL_COMPLETION | Mehanički završetak hale | 30.06.2027 | Datum | 12 mjeseci od starta | Hard | Početak amortizacije zgrade
TL4 | EQUIPMENT_COMMISSIONING | Commissioning mašina + solara | 31.12.2028 | Datum | Nakon montaže | Hard | Najveći tax shield
TL5 | SOLAR_COD | Solar COD | 30.11.2028 | Datum | 1 mjesec prije commissioning | Hard | Ušteda struje 0.3–0.4 mil €/god
TL6 | ISO_CERTIFICATION_DATE | ISO + EN/CE | 31.05.2029 | Datum | Prije COD | Hard | Obavezno za 70 % off-take
TL7 | FIRST_TENDER_SUBMISSION | Prvi tender | 01.04.2029 | Datum | 3 mjeseca prije COD | Soft | Pipeline za revenue
TL8 | PROVISIONAL_ACCEPTANCE_CERT | PAC | 15.06.2029 | Datum | 15 dana prije COD | Hard | Revenue recognition
TL9 | COD | Commercial Operations Date | 01.07.2029 | Datum | Početak proizvodnje | Hard | NAJKRITIČNIJI DATUM – kašnjenje 6 m → IRR -4–6 pp
TL10 | GRACE_PERIOD_END | Kraj grace perioda | 30.06.2029 | Datum | 36 mjeseci od FC | Hard | Početak otplate glavnice
TL11 | FINAL_ACCEPTANCE_CERT | FAC | 31.12.2029 | Datum | 6 mjeseci nakon PAC | Hard | Kraj EPC odgovornosti
3. CAPEX & ASSET LIFE (Ukupno fixed assets 12.850.000 €)
Br | KEY | Opis / Asset Class | Base vrijednost | Jedinica | Useful Life | Deprec. Rate | Tax shield godišnje
CA1 | CAPEX_LAND_PREP | Zemljište + priprema | 38000% | € | ∞ | 0% | 0
CA2 | CAPEX_BUILDING_HALL | Hala 10.000 m² | 7.505.000 | € | 40 god | 2.5% | ~188k €
CA3 | CAPEX_MACHINE_PARK | Kompletan park mašina | 3.945.787 | € | 12 god | 12% | ~470–590k €
CA4 | CAPEX_SOLAR_SYSTEM | Rooftop solar 1.4 MWp | 99400% | € | 25 god | 4% | ~40k € + OPEX ušteda 250–300k €
CA5 | CAPEX_MEP_INFRA | Elektro, HVAC, IT | 1.505.000 | € | 18 god | 5.5% | ~83k €
CA6 | CAPEX_SOFT_COSTS | Projektovanje, ERP, obuka | 66500% | € | 5 god | 20% | ~133k €
CA7 | CONTINGENCY_RESERVE | Rezerva za rizike (9.5 %) | 1.220.000 | € | – | – | Ako se ne potroši → +1–2 pp IRR
CA8 | TOTAL_CAPEX_FIXED | Ukupno fixed assets | 12.850.000 | € | – | – | ~0.9–1.1 mil €/god
4. CAPEX DRAW SCHEDULE + OPERATIONAL PARAMETERS (Motor)
Br | KEY | Opis | Base vrijednost | Jedinica | Komentar / Benchmark | Status | H – Finansijski uticaj / Rizik / Lekcija
CA10 | CAPEX_DRAW_PHASE1_PCT | Faza 1 (2026–mid 2027) | 5500% | % | Hala + priprema + contingency | Hard | ~7.1 mil € outflow
CA11 | CAPEX_DRAW_PHASE2_PCT | Faza 2 (mid 2027–2028) | 3800% | % | Mašine + solar + MEP | Hard | ~4.9 mil €
CA12 | CAPEX_DRAW_PHASE3_PCT | Faza 3 (2029) | 700% | % | Final installation + commissioning | Hard | ~0.9 mil €
OP1 | INSTALLED_CAPACITY | Maksimalni godišnji kapacitet | 7500% | t/god | Realno 63.750 t na 85 % | Hard | Osnova revenue
OP2 | SPECIFIC_ENERGY_CONSUMPTION | Specifična potrošnja struje po toni | 160% | MWh/t | Heavy fab benchmark | Hard | ~120 GWh/god; solar ušteda 250–350k €/god
OP3 | SCRAP_RATE | Tehnološki otpad | 650% | % | Standard CNC + zavarivanje | Hard | ~4.875 t/god → prihod 30–50k €/god
5. REVENUE & RAMP-UP
R1 | TARGET_CAPACITY | Maksimalni kapacitet | 7500% | t/god | Na 85 % utilization | Hard | Realno 63.750 t
R2 | BASE_SALES_PRICE | Prosječna neto prodajna cijena | 185% | €/t | EN/CE sertifikovani tankovi | Hard | Prihod ~118 mil € na punom kapacitetu
R3 | RAMP_UP_Y1 | Ramp-up godina 1 | 4000% | % | Konzervativno | Hard | EBITDA 8–12 %
R4 | RAMP_UP_Y2 | Ramp-up godina 2 | 7000% | % | Standardna optimizacija | Hard | EBITDA 14–17 %
R5 | FULL_CAPACITY_Y3 | Pun kapacitet od godine 3 | 10000% | % | Od 2031. | Hard | EBITDA 18–22 %
R6 | PRICE_GROWTH | Godišnji rast cijene | 300% | % | Od 2031. | Soft | Zaštita od inflacije
6. WORKING CAPITAL
WC1 | DSO | Dani naplate od kupaca | 4500% | dana | B2B tenderi | Hard | Potraživanja ~14.5 mil € na punom kapacitetu
WC2 | DIO | Dani zaliha | 6000% | dana | Čelik + gotovi proizvodi | Hard | Zalihe ~13.6 mil €
WC3 | DPO | Dani plaćanja dobavljačima | 3000% | dana | EU/TR dobavljači | Hard | Obaveze ~6.8 mil €
WC4 | CASH_CONVERSION_CYCLE | CCC | 7500% | dana | DIO + DSO – DPO | Hard | NWC ~20–22 mil € na stabilnom nivou
WC5 | CASH_BUFFER | Minimalna gotovinska rezerva | 2–3 | mjeseca OPEX | IFC/EBRD standard | Hard | Sigurnosni jastuk
7. REVENUE INDEXATION (Štit)
RI1 | STEEL_BASE_INDEX | Bazna cijena čelika (HRC) | 80000% | €/t | Platts / LME Europa Feb 2026 | Hard | Anchor za indeksaciju
RI2 | STEEL_CONTENT_PCT | Udeo čelika u proizvodu | 7000% | % | Heavy fab benchmark | Hard | 70 % direktno utiče na cijenu
RI3 | PASS_THROUGH_COEFFICIENT | Koeficijent prenosa | 100% | – | Full pass-through | Hard | 100 % zaštita marže
RI4 | UPDATE_FREQUENCY | Učestalost ažuriranja | Q | text | Kvartalno | Hard | Optimalno za B2B
RI5 | STEEL_PRICE_VOLATILITY | Očekivana volatilnost | ±20 | % | Povijesna 2020–2026 | Soft | Sa pass-through rizik ≈0 %
RI6 | HEDGING_LAG | Kašnjenje prenosa | 100% | kvartal | Realan kompromis | Hard | Privremeni pritisak 1–2 % EBITDA
RI7 | TARGET_EBITDA_MARGIN | Ciljana EBITDA marža | 1650% | % | Post-indeksacije | Hard | Zaključana marža
8. FINANCING & CAPITAL STRUCTURE
Br | KEY | Opis | Base vrijednost | Jedinica | Komentar | Status | H – Finansijski uticaj / Rizik / Lekcija
F1 | EQUITY_SHARE | Učešće equity-a | 3500% | % | Skin in the game | Hard | ~5.27 mil €
F2 | GRANT_SHARE | Grant (IPA III / WBIF) | 1500% | % | Green + industrial | Hard | ~2.26 mil € besplatno
F3 | DEBT_SHARE | Dug | 5000% | % | EBRD/IFC | Hard | ~7.525 mil €
F4 | INT_RATE | Kamatna stopa | 600% | % | EURIBOR + margin | Hard | ~451k €/god
F5 | LOAN_TENOR | Tenor kredita | 1000% | godina | + 36 m grace | Hard | Maturity matching
F6 | GRACE_PERIOD | Grace period | 3600% | mjeseci | Do COD | Hard | Štit u ramp-upu
F8 | DSCR_MIN | Min DSCR covenant | 130% | x | IFC/EBRD | Hard | Model pokazuje 1.74x
9. COST STRUCTURE SPLIT (CFO Optimizacija)
Br | KEY | Kategorija | % od COGS/OPEX | Iz nos na punom kapacitetu | Napomena | Status | H – Finansijski uticaj / Rizik / Lekcija
CS1 | MATERIAL_COST_PCT | Materijali (čelik) | 65–70 | ~7.5–8.1 mil € | Full pass-through | Hard | Najveći rizik – zaštićen indeksacijom
CS2 | LABOR_COST_PCT | Radna snaga | 10–12 | ~1.15–1.4 mil € | 55 radnika | Hard | Stabilno u CG
CS3 | ENERGY_COST_PCT | Energija | 5–7 | ~0.6–0.8 mil € | Solar pokriva 10–15 % | Hard | Najjači lever za marginu
CS5 | FIXED_OPEX_PCT | Fiksni troškovi | 5–8 | ~0.6–0.9 mil € | Maintenance + insurance | Hard | Stabilno
CS6 | TOTAL_COGS_PCT | Ukupni COGS | 10000% | ~11.5–12.5 mil € | Ciljana EBITDA 18–22 % | Hard | Osnova za DSCR
10. ESG & IMPACT
ESG1 | CO2_SAVINGS | Godišnja ušteda CO₂ | 52000% | t/god | Solar + efikasnost | Hard | Grant + greenium
ESG2 | JOBS_CREATED | Nova radna mjesta | 55 + 30–40 | broj | Direktno + indirektno | Hard | Socijalni KPI za grantove
ESG3 | ENERGY_COST_REDUCTION | Smanjenje kupljene energije | 3000% | % | Solar + optimizacija | Hard | OPEX ušteda 250–350k €/god
11. RISK & DECOMMISSIONING
RD1 | INSURANCE_PREM | Osiguranje | 50% | % CAPEX | Property + BI + MB | Hard | Transfer rizika
RD2 | BI_COVERAGE | Business Interruption | 600% | mjeseci | Pokriva rate + fiksni troškovi | Hard | Keš jastuk
RD3 | DECOMM_COST | Dekomisija | 3% | % assets | IAS 37 ARO | Hard | DNSH princip
RD6 | MAINTENANCE_CAPEX | Održavanje | 2–3 | % equipment | Preventivno | Hard | Sprječava impairment
RD7 | DSRA | Debt Service Reserve Account | 600% | mjeseci | IFC/EBRD standard | Hard | Zaštita DSCR
12. SCENARIOS & SENSITIVITY (za banku)
| Scenarij | Ključne promjene (u odnosu na base) | Equity IRR | Min DSCR (Y1–Y3) | NPV @8 % (mil €) | Bankarski komentar / Lekcija
| Base Case | COD 01.07.2029, steel 800 €/t, pass-through 1.0, energy 1.6 MWh/t, TRY 51.7, solar 100 % | 26% | 1.74x | 11.2 | Realističan, bankabilan, grant-eligible
| Downside – COD Delay 6m | COD → 01.01.2030, grace skraćen, CAPEX inflacija +4 %, ramp-up kasni | 20.8% | 0.92x | 4.1 | Najkritičniji rizik. EPC LD + equity cure obavezan. Contingency 9.5 % spašava
| Downside – Steel Shock | HRC +25 % (na 1.000 €/t), pass-through pada na 0.8 u Y1 | 22.4% | 1.18x | 6.8 | EBITDA -9 %. Sa RI3=1.0 → uticaj <1 pp. Full indeksacija obavezna
| Downside – TRY Weakness | TRY -18 % (na 61), Machine Park +0.55 mil € CAPEX | 24.1% | 1.35x | 8.9 | Hedžuj 80 % u EUR – bez hedža IRR pada ispod 22 %
| Downside – Energy Spike | Struja +22 % (bez solara), energy 7.5 % COGS | 24.7% | 1.42x | 9.3 | Solar + PPA = ključni štit. Ušteda 280k €/god spašava marginu
| Combined Downside | Delay 6m + HRC +25 % + TRY -18 % + energy +15 % (najgori realni slučaj) | 18.9% | 1.05x | 2.8 | IRR još uvijek > WACC 9.5 %. DSCR blizu breakevena → DSRA + equity cure
| Upside – Grant + Ramp | Grant 20 %, ramp-up Y1 55 %, solar yield +12 %, full off-take od Y2 | 31.2% | 2.15x | 18.4 | Green premium + niža kamata (greenium -0.75 %)
| Break-even | Min potrebno za IRR = WACC 9.5 % | 9.5% | 1.30x | 0 | Volume 58 kt/god ili steel pass-through ≥0.65

## CAPEX_MASTER (2)
ARS METAL INDUSTRIES DOO – CAPEX MASTER
Version 2.0 ¦ Datum: 26.02.2026 ¦ CFO: Onur
ASSUMPTIONS
TOTAL PROJECT COST (bez PDV) | Kategorija | Subtotal bez PDV (€) | Subtotal sa PDV (€) | % od ukupnog CAPEX | [6 empty] | PDV stopa | 21%
1. Land & Site
2. Civil Works
3. Machinery (ARS linija)
4. Installation & Commissioning
5. Engineering & Permits
6. Contingency (7%)
TOTAL CAPEX (bez WC) |  |  |  | 100%
7. Working Capital (start-up)
GRAND TOTAL INVESTICIJA |  |  |  | 100%
FUNDING STRUCTURE
Equity (Hamzi + sopstveno) | 40%
Bank Debt | 55%
Grant (EU/IPA opcionalno) | 5%
UKUPNO FINANSIRANJE
CAPEX ID | Category | Subcategory | Description | Supplier | Unit | Qty | Unit Cost € | Total bez PDV | PDV 21% | Total sa PDV | Year | Useful Life | Funding Source | Notes / Rizik
1.1 | 1. Land & Site | Acquisition | Kupovina parcele (cca 15.000–18.000 m² bruto, uzeto 22.500 m²) | - | m² | 22500 | 55 |  |  |  | 2026 | 999 | Equity | Raspon 750k–1.1M €; ~45–65 €/m² po oglasima Tuzi 2026; proveri katastar
1.2 | 1. Land & Site | Acquisition | Pravne i Notarske takse (prenos apsolutnih prava, upis u katastar) | - | % | 2% |  |  |  | 2026 | 999 | Equity | 1–3% vrednosti parcele; poreski i katastarski troškovi
1.3 | 1. Land & Site | Inženjering | Geomehaničko ispitivanje (bušotine i ispitivanje nosivosti tla) | - | kom | 1 | 7500 |  |  |  | 2026 | 999 | Equity | 5–10k €; ključno za heavy duty podove i kraneve
1.4 | 1. Land & Site | Priprema | Priprema i ravnanje terena (skidanje humusa, nasipanje tampona, drenaža) | - | m² | 16500 | 5 |  |  |  | 2026 | 40 | Equity | 60–100k € ukupno; zavisi od terena
1.5 | 1. Land & Site | Takse | Komunalna naknada za opremanje (Opština Tuzi, zona I) | - | m² | 10000 | 48.81 |  |  |  | 2026 | 999 | Equity | Po Odluci Opštine Tuzi ~48.81 €/m²; proveri subvencije za industriju
1.6 | 1. Land & Site | Infrastruktura | Energetski priključak – izgradnja trafostanice i priključak na mrežu (1MW+) | - | kom | 1 | 65000 |  |  |  | 2026 | 30 | Debt | 50–80k €; može biti više za 1MW+; CEDIS projekti pokazuju velika ulaganja
1.7 | 1. Land & Site | Infrastruktura | Hidrotehnička instalacija (priključak na vodovod + separatori ulja/masti) | - | kom | 1 | 27500 |  |  |  | 2026 | 30 | Debt | 20–35k €; obavezno za fabriku (ulja od transformatora)
1.8 | 1. Land & Site | Sigurnost | Ograda i obezbeđenje (industrijska ograda, kapije za šlepere, video nadzor) | - | m | 800 | 50 |  |  |  | 2026 | 20 | Equity | 30–50k €; dužina ograde ~800m za parcelu 22.5k m²
1.9 | 1. Land & Site | Logistika | Pristupne saobraćajnice (asfalt za teški teretni saobraćaj) | - | m² | 2000 | 30 |  |  |  | 2026 | 15 | Equity | 40–70k €; širina 6–8m, debljina za šlepere
2.1 | 2. Civil Works | Noseća konstrukcija | Čelična primarna konstrukcija (stubovi, grede, veze) | - | m² | 10000 | 200 |  |  |  | 2026 | 25 | Debt | 180–260 €/m²; za kraneve može više
2.2 | 2. Civil Works | Krov i fasada | Sendvič paneli PIR (80–100 mm izolacija) | - | m² | 12000 | 50 |  |  |  | 2026 | 20 | Debt | PIR za bolji ESG i grant
2.3 | 2. Civil Works | Heavy Duty podovi | Pojačani beton + armatura + zaptivke za ulja (nosivost za kraneve/tankove) | - | m² | 10000 | 120 |  |  |  | 2026 | 30 | Debt | Ne štedjeti – ključno za dinamičko opterećenje
2.4 | 2. Civil Works | Administrativni dio | Kancelarije + svlačionice + kantina (viši standard) | - | m² | 1000 | 380 |  |  |  | 2026 | 25 | Equity | Energy Class A/B preporučeno za EU grantove
2.5 | 2. Civil Works | Vrata i prozori | Industrijska sekcijska vrata + prozori | - | set | 1 | 90000 |  |  |  | 2026 | 15 | Debt | Door Height 8–10 m za visoke hale
2.6 | 2. Civil Works | Basic Utilities | Vodovod, kanalizacija, elektro osnovno, gromobran, LED osvjetljenje | - | lot | 1 | 120000 |  |  |  | 2026 | 20 | Debt | Osnovno prije mašina
2.7 | 2. Civil Works | Završni radovi | Boje, opšivke, čišćenje gradilišta | - | lot | 1 | 60000 |  |  |  | 2026 | 15 | Equity | Manji troškovi
2.8 | 2. Civil Works | Temelji za mašine/kraneve | Temelji + šine za kraneve + sidrenje (kritično!) | - | lot | 1 | 250000 |  |  |  | 2026 | 30 | Debt | Najveći rizik – geomehanika
2.9 | 2. Civil Works | Vatrootporni premazi | Industrial coating / zaštita metala | - | m² | 10000 | 5 |  |  |  | 2026 | 10 | Debt | 30–80k € za metalnu industriju
2.10 | 2. Civil Works | Požarna zaštita | Sprinkler ili hidrantska mreža | - | lot | 1 | 110000 |  |  |  | 2026 | 20 | Debt | 70–150k €; banke insistiraju
2.11 | 2. Civil Works | HVAC / Ventilacija | Industrijska ventilacija (za zavarivanje + emisije) | - | lot | 1 | 140000 |  |  |  | 2026 | 15 | Debt | 80–200k €; specijalno za fabriku
2.12 | 2. Civil Works | Projektovanje i nadzor | Inženjering, dozvole, stručni nadzor (soft costs) | - | % | 6% |  |  |  | 2026 | 5 | Debt | 5–8% od Civil Works; obavezno za EU
3.1 | 3. Machinery (ARS linija) | Cutting | Fiber Laser (visoka snaga 6–12kW, large format) | Turska/Kina | kom | 1 | 300000 |  |  |  | 2026 | 7 | Debt | 250k–450k €; precizno sečenje limova
3.2 | 3. Machinery | Cutting | CNC Plasma (large format za deblje ploče) | - | kom | 1 | 100000 |  |  |  | 2026 | 7 | Debt | 80k–130k €; grublja obrada
3.3 | 3. Machinery | Bending | Press Brake (400t+ tonaža, CNC) | - | kom | 1 | 180000 |  |  |  | 2026 | 7 | Debt | 150k–220k €; savijanje stranica/ojacanja
3.4 | 3. Machinery | Forming | Corrugated Wall Line (specijalizovana za rebraste zidove) | Turska | linija | 1 | 450000 |  |  |  | 2026 | 10 | Debt | 350k–550k €; srce ARS proizvodnje
3.5 | 3. Machinery | Welding | Welding Robots (ćelija sa pozicionerom, multi-robot) | EU/Turska | ćelija | 1 | 280000 |  |  |  | 2026 | 7 | Debt | 200k–350k €; za uljno-nepropusnost
3.6 | 3. Machinery | Surface Treatment | Painting & Sandblasting (automatska linija C4/C5) | - | linija | 1 | 220000 |  |  |  | 2026 | 10 | Debt | 180k–280k €; zaštita od korozije
3.7 | 3. Machinery | Lifting | Overhead Cranes (2x20t + 2x10t, double girder) | - | set | 1 | 140000 |  |  |  | 2026 | 15 | Debt | 120k–170k €; prenos masivnih sudova
3.8 | 3. Machinery | Testing | Testing Bench (Air/Oil pressure test za nepropusnost) | - | kom | 1 | 50000 |  |  |  | 2026 | 10 | Debt | 40k–60k €; provera pod pritiskom
3.9 | 3. Machinery | Logistics | Forklifts (1x10t heavy + 2x3t) | - | set | 1 | 110000 |  |  |  | 2026 | 7 | Debt | 90k–130k €; interna logistika
4.1 | 4. Installation & Commissioning | Transport & Logistika | Prevoz vangabaritnih mašina (od luke Bar/granice do Tuzi) | - | lot | 1 | 32500 |  |  |  | 2026 | 999 | Debt | 20–45k €; rizik carine i kašnjenja
4.2 | 4. Installation & Commissioning | Supervizori | Inženjerski supervizori (dnevnice, letovi, smeštaj za strane montažere) | - | lot | 1 | 45000 |  |  |  | 2026 | 5 | Debt | 30–60k €; obavezno za specijalne mašine
4.3 | 4. Installation & Commissioning | Lokalna radna snaga | Angažovanje pomoćnih radnika, kranista, električara tokom montaže | - | lot | 1 | 15000 |  |  |  | 2026 | 999 | Equity | 10–20k €; lokalna snaga za smanjenje troškova
4.4 | 4. Installation & Commissioning | Kalibracija & Testiranje | Precizno podešavanje lasera, presa, robota + inicijalni testovi | - | lot | 1 | 20000 |  |  |  | 2026 | 5 | Debt | 15–25k €; ključno za preciznost
4.5 | 4. Installation & Commissioning | Obuka operatera | Sertifikacija zavarivača + obuka za CNC/laser/robote | - | lot | 1 | 22500 |  |  |  | 2026 | 5 | Equity | 15–30k €; može biti dio grantova
4.6 | 4. Installation & Commissioning | Nulta serija (Trial Run) | Materijal (lim), energenti, otpaci za prve test tankove | - | lot | 1 | 15000 |  |  |  | 2026 | 999 | Equity | 10–20k €; valley of death faza
5.1 | 5. Engineering & Permits | Glavni projekat | Arhitektonski, konstruktivni, elektro i mašinski projekti | - | lot | 1 | 55000 |  |  |  | 2026 | 5 | Equity | 40–70k €; za halu + fabriku
5.2 | 5. Engineering & Permits | Revizija projekta | Obavezna revizija glavnog projekta licencirane kuće | - | lot | 1 | 7500 |  |  |  | 2026 | 5 | Equity | 5–10k €; po Zakonu o planiranju i izgradnji
5.3 | 5. Engineering & Permits | EIA (Procena uticaja) | Elaborat o zaštiti životne sredine (farbanje, peskarenje) | - | lot | 1 | 5000 |  |  |  | 2026 | 5 | Equity | 3–7k €; obavezno za EPA CG
5.4 | 5. Engineering & Permits | Stručni nadzor | Licencirani inženjeri – nadzor tokom gradnje | - | % | 1.8% |  |  |  | 2026 | 5 | Debt | 1.5–2% od radova; obavezno po zakonu
5.5 | 5. Engineering & Permits | PPZ i Zaštita na radu | Elaborati zaštite od požara, bezbednosti radnika | - | lot | 1 | 6000 |  |  |  | 2026 | 5 | Equity | 4–8k €; obavezno za fabriku
5.6 | 5. Engineering & Permits | Dozvole i takse | Prijava gradnje, takse za priključke, ekološka saglasnost | - | lot | 1 | 17500 |  |  |  | 2026 | 999 | Equity | 10–25k €; Opština Tuzi
5.7 | 5. Engineering & Permits | Geodetske usluge | Obeležavanje parcele, snimanje instalacija, završni snimak | - | lot | 1 | 4000 |  |  |  | 2026 | 999 | Equity | 3–5k €; standardno za parcelu
7.1 | 7. Working Capital (Start-up) | Inicijalna zaliha sirovina | Čelični limovi, profili, boja (zaliha za prva 3 mjeseca – ~50–100 tona limova) | - | lot | 1 | 225000 |  |  |  | 2026 | 999 | Equity | 150–300k €; buffer za cijene čelika
7.2 | 7. Working Capital | Plate (Payroll Buffer) | Neto plate + porezi/doprinosi za sve zaposlene (prva 3–4 mjeseca) | - | lot | 1 | 100000 |  |  |  | 2026 | 999 | Equity | 80–120k €; ~20–40 radnika
7.3 | 7. Working Capital | Troškovi energije (OPEX buffer) | Struja (mrežna + solarni dopuna), voda, komprimovani vazduh | - | lot | 1 | 22500 |  |  |  | 2026 | 999 | Equity | 15–30k €; ~150–300k kWh/mj
7.4 | 7. Working Capital | Rezervni delovi i potrošni materijal | Sočiva za laser, dizne, gasovi za varenje, žica | - | lot | 1 | 30000 |  |  |  | 2026 | 999 | Equity | 20–40k €; kritično za kontinuitet
7.5 | 7. Working Capital | Marketing i Prodaja | Sajmovi, katalogi, putni troškovi, uzorci za kupce | - | lot | 1 | 15000 |  |  |  | 2026 | 999 | Equity | 10–20k €; B2B ugovaranje
7.6 | 7. Working Capital | Osiguranje fabrike i opreme | Polisa osiguranja imovine, opreme, zaposlenih (prva rata) | - | lot | 1 | 10000 |  |  |  | 2026 | 999 | Equity | 5–15k €; 0.3–0.8% vrednosti imovine

## Machine Park Detail
ARS Metal Industries DOO Version 1.0 Date: 25.02.2026
Red. br. | Proizvođač / Model | Opis / Specifikacija | Količina | Jed. | Cijena po jed. (€) | Ukupno (€) | Poreska grupa | Stopa (%) | Rač. vijek (god.) | Napomena
1 | UNI-MAK | 1600mm DALGADUVAR ÜRETİM HATTI (kompletna linija) | 1 | kom | 900000 |  | II | 10 | 10 | Glavna linija
2 | SLS MECANO | ROBOT KAYNAK | 1 | kom | 80000 |  | III | 15 | 7 | Specijalna
3 | - | ABKANT BÜKÜM MAKİNASI | 1 | kom | 85000 |  | II | 10 | 10 | -
4 | - | PUNTA MAKİNASI | 1 | kom | 96000 |  | II | 10 | 10 | -
5 | SAYMAK | GİYOTİN MAKAS | 1 | kom | 10740 |  | II | 10 | 10 | -
6 | MVD | ABKANT PRES | 1 | kom | 150750 |  | II | 10 | 10 | -
7 | NKN | 8 kW LAZER KESİM | 1 | kom | 290000 |  | III | 15 | 7 | Specijalna
8 | NKN | 15 kW LAZER KESİM | 1 | kom | 340000 |  | III | 15 | 7 | Specijalna
9 | NKN | 4 kW BORU LAZER KESİM | 1 | kom | 335000 |  | III | 15 | 7 | Specijalna
10 | ÖZFATİHLER VİNÇ | 10 ton čift kiriş tavan vinç | 10 | adet |  | 350000 | IV | 20 | 10 | Teška oprema
11 | TORO VİNÇ | 40 ton čift kiriş tavan vinç | 3 | adet |  | 225000 | IV | 20 | 10 | Teška oprema
12 | TORO VİNÇ | 5 ton pergol vinç | 15 | adet |  | 210000 | IV | 20 | 10 | Teška oprema
13 | GENPOWER | 1000 kW kabinski dizel generator | 1 | kom | 72085 |  | IV | 20 | 10 | Backup
14 | ASTOR | 1600 kW köşk pano | 1 | kom | 53862 |  | II | 10 | 10 | Elektro
15 | BİNMAK | Boru bükme makinesi | 1 | kom | 14600 |  | II | 10 | 10 | -
16 | ADS | Kazan basınç hava test ünitesi | 1 | kom | 40000 |  | II | 10 | 10 | Test
17 | YILDIZ KARDEŞLER | Otomatik kumlama hattı | 1 | kom | 75000 |  | III | 15 | 8 | Priprema
18 | ENDÜSTRİYEL | Taylor saplama kaynak makinesi | 1 | kom | 6700 |  | II | 10 | 10 | Zavarivanje
19 | HİLALSAN | Hidrolik kombine makas | 1 | kom | 49500 |  | II | 10 | 10 | -
20 | LINDE | Akülü forklift 8 ton | 2 | adet |  | 304000 | IV | 20 | 5 | Logistika
21 | LINDE | Akülü forklift 2 ton | 4 | adet |  | 120000 | IV | 20 | 5 | Logistika
22 | İESMAK | Yaş boya tesisi + kapak i konveyör hattı | 1 | kom | 120000 |  | II | 10 | 10 | Bojenje
23 | TAMSAN | Vidali hava kompresör (tank + kurutucu) | 1 | kom | 17550 |  | II | 10 | 10 | Pneumatika
UKUPNO MAKINA PARKI
Grupa | Iznos (€)
II
III
IV
UKUPNO

## Timeline & Sensitivity
ARS METAL INDUSTRIES DOO – CAPEX MASTER
VREMENSKI PLAN PROJEKTA – TIMELINE & GANTT
Ukupno trajanje: 30–36 mjeseci (od Q2 2026 do Q3/Q4 2028)
Faza / Aktivnost | 2026 Q2 | 2026 Q3 | 2026 Q4 | 2027 Q1 | 2027 Q2 | 2027 Q3 | 2027 Q4 | 2028 Q1 | 2028 Q2 | 2028 Q3 | 2028 Q4 | % CAPEX | Iznos (€) | Komentar / Rizik
Kupovina zemljišta & dozvole | ████ | ████ | [9 empty] | 0.05 | 625000 | Rizik kašnjenja dozvola
Projektovanje & studije | ████ | ████ | ████ | [8 empty] | 0.03 | 375000 | EIA Feb 2026
Građevinski radovi |  |  | ████ | ████ | ████ | ████ | ████ | ████ |  |  |  | 0.35 | 4375000 | Seizmički uplift
Nabavka & isporuka mašina |  |  | ████ | ████ | ████ | ████ | ████ | ████ |  |  |  | 0.3 | 3750000 | TRY rizik
MEP instalacije |  |  |  |  | ████ | ████ | ████ | ████ | ████ |  |  | 0.12 | 1500000 | Kritična faza
Soft costs |  |  | ████ | ████ | ████ | ████ | ████ | ████ |  |  |  | 0.1 | 1250000 | ERP + sertifikati
Commissioning | [6 empty] | ████ | ████ | ████ |  |  | 0.05 | 625000 | Start Q3/Q4 2028
SENZITIVNOST / SCENARIJI (Sensitivity Analysis)
Scenarij | Promjena | Utjecaj na CAPEX (€) | Utjecaj na WC (€) | Ukupni potrebni iznos (€) | Rizik / Mitigacija
Base Case | — | 12500000 | 2200000 | 14700000 | —
TRY deprecijacija +20% | FX_STRESS_20 | 789157 | 0 | 789157 | 80% hedžovano
Građevinski troškovi +15% | +15% civil | 975000 | 0 | 975000 | Contingency 15%
Kašnjenje 6 mjeseci | +6 mjeseci | 450000 | 400000 | 850000 | Plate + eskalacija
WC potreban +20% | +20% WC | 0 | 440000 | 440000 | Revolving linija
Worst Case | Kombinovano | 2214157 | 840000 | 3054157 | Equity buffer
Svi scenariji su konzervativni. Worst Case pokriven equity-jem i contingency-jem od 9.5%.

## WC Cash Flow
ARS METAL INDUSTRIES DOO – CAPEX MASTER
Version 2.0 ¦ Datum: 26.02.2026 ¦ CFO: Onur
WORKING CAPITAL CASH FLOW – PRVA GODINA
Početni WC: 2.200.000 € ¦ Početak proizvodnje: septembar 2028
Mjesečni pregled (u €)
Stavka | M1 (Sep 28) | M2 (Okt) | M3 (Nov) | M4 (Dec) | M5 (Jan 29) | M6 (Feb) | M7 (Mar) | M8 (Apr) | M9 (Maj) | M10 (Jun) | M11 (Jul) | M12 (Avg) | Ukupno 12 m
Početni WC saldo | 2200000
Plate (55 ljudi) | 58000 | 70000 | 90000 | 110000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000
Sirovina & materijal | 120000 | 200000 | 350000 | 500000 | 650000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000
Rezervni dijelovi & održavanje | 20000 | 25000 | 30000 | 35000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
Energija | 40000 | 55000 | 70000 | 85000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
Ostali operativni troškovi | 30000 | 40000 | 50000 | 60000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000
Ukupni mjesečni odlivi
Prihodi od prodaje | 0 | 0 | 0 | 0 | 200000 | 500000 | 800000 | 1000000 | 1200000 | 1400000 | 1600000 | 1800000
Naplata potraživanja (DSO 60 dana) | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 300000 | 600000 | 1000000 | 1400000 | 0
Ukupni mjesečni prilivi
Neto cash flow mjesec
Kumulativni WC saldo
Napomene:
Početni WC saldo pokriva ~5.5 mjeseci operacija bez prihoda
Prvi značajniji priliv očekuje se u 5. mjesecu
Najveći odliv: sirovine + plate
Ako DSO >60 dana → potreban dodatni WC 300–500k €
Mitigacija: factoring + duži DPO

## REVENUE_COGS
ARS METAL INDUSTRIES – REVENUE & COGS PROJEKCIJA (v2.5)
Datum: 26.02.2026
Ključni inputi (veži na Assumptions)
Parametar | Vrijednost
MAX_CAPACITY_TPY
RAMP_UP_Y1
RAMP_UP_Y2
RAMP_UP_Y3
BASE_SALES_PRICE_EUR_PER_T
SALES_PRICE_INFL
TARGET_GROSS_MARGIN
COGS_INFL
Godina | Prodaja (t) | Cijena €/t | Prihod (€) | COGS €/t | COGS (€) | Bruto marža (€) | Bruto marža %
2029
2030
2031
2032
2033
2034
2035
2036
2037
2038

## OPEX_DETAIL
ARS METAL INDUSTRIES – OPEX DETAIL (v2.5)
Datum: 26.02.2026
OPEX model: total OPEX = Revenue * FIXED_OPEX_PCT, uz inflaciju.
FIXED_OPEX_PCT
INF_OPEX
Godina | Total OPEX (€) | Admin & HR (30%) | Maintenance (20%) | Utilities (15%) | Insurance (5%) | SG&A (30%)
2029
2030
2031
2032
2033
2034
2035
2036
2037
2038

## CAPEX_CASHFLOW
ARS METAL INDUSTRIES – CAPEX CASH FLOW (godišnji) (v2.5)
Izvor: CAPEX_MASTER (2)
Godina | Land & Site | Civil Works | Machinery | Installation | Engineering | Contingency | Total CAPEX (bez WC) | Cumulative
2026
2027
2028

## DEBT_SCHEDULE
ARS METAL INDUSTRIES – DEBT SCHEDULE & DSCR (v2.5)
Datum: 26.02.2026
Ukupan debt
Kamatna stopa
Grace period (mjeseci)
Tenor (mjeseci)
Mjesečni anuitet (posle grace)
Godina | Početni saldo | Drawdown | Kamata | Principal | Otplata ukupno | Krajnji saldo | DSCR
2026 | 0
2027
2028
2029
2030
2031
2032
2033
2034
2035
2036
2037
2038

## INTEGRATED_P&L_BS_CF
ARS METAL INDUSTRIES – INTEGRATED P&L + BS + CF (v2.5)
Datum: 26.02.2026
Svi ključni inputi vuku iz Assumptions + CAPEX_MASTER. Provjeri CHECKS_&_CONTROLS za greške.
Godina | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038
Revenue
COGS
Gross Profit
OPEX
EBITDA
Depreciation
EBIT
Interest
EBT
Tax
Net Profit
Operating CF
Investing CF
Financing CF
Net Cash Flow
Ending Cash

## DASHBOARD
ARS METAL INDUSTRIES – CFO DASHBOARD (Bank-Ready) (v2.5)
Automatski KPI + grafici (iz INTEGRATED / CAPEX / DEBT).
TOTAL CAPEX (bez PDV)
GRAND TOTAL INVESTICIJA (sa WC, bez PDV)
Equity (EUR)
Debt (EUR)
Grant (EUR)
Min DSCR
Revenue @2031
EBITDA Margin @2031

## CHECKS_&_CONTROLS
CHECKS & CONTROLS – Model QA (v2.5)
Crveno = kritično (banke će odbiti). Žuto = upozorenje.
Kontrola | Formula | Status
VAT rate defined
Sources = Uses (Debt+Equity+Grant vs Grand Total)
CAPEX subtotal sum
Min DSCR >= 1.30
Count of '#NAME?' strings | 1