## 00_Index
ARS Business Plan Harmonization & Forensic Review
Compiled from chapters 1.1 to 3.3. Purpose: harmonize outputs into Document List, Task Register, Financial Map, OKR Strategy, and a forensic issue log.
Workbook purpose | Convert narrative into execution and control architecture; flag unsupported claims, contradictions and evidence gaps.
Review stance | Forensic / zero-tolerance / evidence-first.
Scope covered | Sections 1.1 to 3.3 of the current business plan draft.
Primary outputs | Document_List, Task_Register, Financial_Map, Strategy_OKR, Issue_Log, Evidence_Tracker, Chapter_Summary.
Important caveat | This workbook harmonizes the text provided in chat. It does not independently verify external facts unless separately sourced.
KPI | Formula / Value | Comment
Chapters covered |  | Should equal analyzed sections
Documents extracted |  | Document rows
Tasks extracted |  | Task rows
Financial map rows |  | Finance rows
Strategy / OKR rows |  | Strategy rows
Forensic issues flagged |  | Issue count
Color / Style | Meaning | Application
Blue text | Hardcoded input | Editable assumptions
Black text | Formula / derived | Calculated outputs
Green text | Internal linked / imported | Pulled from another sheet
Light red fill | Critical forensic issue / immediate action | High severity
Amber fill | Review / caution | Needs validation before external use

## Chapter_Summary
Chapter Summary
One-line harmonized view per chapter
Chapter | Title | Documents | Tasks | Financial Rows | Strategy Rows | Critical Issues | Status | Audit Note
1.1 | Project Overview and Strategic Objectives | 8 | 5 | 10 | 6 | 1 | Reviewed | Narrative harmonized; external evidence still required for flagged claims.
1.2 | Investment Summary and Funding Requirements | 8 | 5 | 7 | 6 | 2 | Reviewed | Narrative harmonized; external evidence still required for flagged claims.
1.3 | Market Opportunity and Competitive Positioning | 9 | 5 | 8 | 6 | 3 | Reviewed | Narrative harmonized; external evidence still required for flagged claims.
1.4 | Financial Highlights and Return Profile (2026-2029) | 8 | 5 | 12 | 6 | 2 | Reviewed | Narrative harmonized; external evidence still required for flagged claims.
1.5 | National and EU Strategic Value | 8 | 5 | 6 | 7 | 1 | Reviewed | Narrative harmonized; external evidence still required for flagged claims.
2.1 | National Industrial Relevance | 8 | 5 | 6 | 6 | 2 | Reviewed | Narrative harmonized; external evidence still required for flagged claims.
2.2 | Alignment with Energy Infrastructure Needs | 8 | 5 | 8 | 6 | 2 | Reviewed | Narrative harmonized; external evidence still required for flagged claims.
2.3 | Export and Industrial Capacity Impact | 8 | 5 | 7 | 6 | 1 | Reviewed | Narrative harmonized; external evidence still required for flagged claims.
3.1 | Legal Structure and Registration | 9 | 5 | 6 | 6 | 1 | Reviewed | Narrative harmonized; external evidence still required for flagged claims.
3.2 | Ownership and Governance Model | 9 | 5 | 6 | 6 | 0 | Reviewed | Narrative harmonized; external evidence still required for flagged claims.
3.3 | Management and CFO Control Framework | 9 | 7 | 7 | 7 | 0 | Reviewed | Narrative harmonized; external evidence still required for flagged claims.

## Document_List
Document List
Master list of documents implied by chapters 1.1-3.3
Chapter | Document | Purpose | Owner | Priority | Status | Due_Date | Forensic_Note | Source_Section
1.1 | Project Overview | Opis projekta investitorima | Management | High | Open |  | Core project narrative and industrial scope | 1.1
1.1 | Strategic Objectives Plan | Definisanje ciljeva i KPI | Management | High | Open |  | Capacity, DSCR, ROI, export, ISO goals | 1.1
1.1 | Location & Logistics Analysis | Analiza prednosti lokacije | Project Development Team | Medium | Open |  | Tuzi / Podgorica / Bar multimodal logic | 1.1
1.1 | Production Capacity Plan | Plan ramp-up proizvodnje | Technical Director | High | Open |  | 10,000 t/year target ramp-up | 1.1
1.1 | Energy Strategy (Solar 1 MWp) | Smanjenje troškova energije | Engineering | High | Open |  | Solar integration and energy resilience | 1.1
1.1 | Financial KPI Framework | DSCR, ROI i finansijski ciljevi | CFO | High | Open |  | Minimum covenant logic | 1.1
1.1 | Export Market Strategy | DACH tržišna strategija | Sales Director | High | Open |  | OEM and target market focus | 1.1
1.1 | Certification Plan | ISO / EN compliance path | Quality Manager | High | Open |  | ISO 9001/14001/45001 roadmap | 1.1
1.2 | Investment Structure Plan | Prikaz izvora finansiranja | CFO | High | Open |  | Equity/debt/grant/subordinated mix | 1.2
1.2 | Sources & Uses of Funds | Raspodjela kapitala | CFO | High | Open |  | 10.33M balanced uses | 1.2
1.2 | CAPEX Allocation Plan | Detalji investicije | CFO + Technical | High | Open |  | 8.0M capex detail | 1.2
1.2 | Working Capital Strategy | Plan likvidnosti | CFO | High | Open |  | 2.0M WC logic | 1.2
1.2 | Grant Application Dossier | Aplikacija za EU fondove | CFO / Consultant | High | Open |  | IPA III / WBIF / RGF narrative | 1.2
1.2 | Bank Financing Package | Dokumentacija za banke | CFO | High | Open |  | Debt approval process | 1.2
1.2 | Financial Sustainability Model | DSCR and ROI analysis | CFO | High | Open |  | Base/no-grant resilience | 1.2
1.2 | Contingency Plan | Plan rezervi i rizika | CFO | Medium | Open |  | 0.33M reserve usage | 1.2
1.3 | Market Opportunity Analysis | Analiza EU potražnje | Sales / Strategy | High | Open |  | Demand gap and transformer market | 1.3
1.3 | Competitive Landscape Study | Analiza konkurencije | Strategy Team | High | Open |  | EU vs Asia comparison | 1.3
1.3 | Near-shoring Advantage Report | Prednosti lokacije | Development Team | Medium | Open |  | Transit, carbon, lead time benefits | 1.3
1.3 | Value Proposition Document | Definicija tržišne vrijednosti | Management | High | Open |  | Reliability + speed + traceability | 1.3
1.3 | Raw Material Risk Policy | Upravljanje cijenom čelika | CFO / Procurement | High | Open |  | Index-linked pricing | 1.3
1.3 | OEM Partnership Strategy | Plan partnerstava | Sales Director | High | Open |  | Preferred supplier route | 1.3
1.3 | Go-to-Market Strategy | Strategija prodaje | Sales Director | High | Open |  | OEM + DSO/TSO tender path | 1.3
1.3 | Tender Qualification Strategy | ISO / EN 1090 barriers | Quality Manager | High | Open |  | Qualification gate | 1.3
1.3 | Pricing Strategy Model | Index-linked pricing model | CFO / Sales | High | Open |  | Margin protection | 1.3
1.4 | Financial Projection Model | 2026-2029 projections | CFO | High | Open |  | Revenue, EBITDA, DSCR path | 1.4
1.4 | Revenue Forecast Plan | Sales and utilization forecast | CFO / Sales | High | Open |  | Utilization ramp | 1.4
1.4 | EBITDA Analysis | Profitability bridge | CFO | High | Open |  | 12% to 26% | 1.4
1.4 | Debt Service Plan | Grace period and amortization plan | CFO | High | Open |  | Interest-only ramp | 1.4
1.4 | NPV & Payback Analysis | Return profile | CFO | High | Open |  | 5-year payback claim | 1.4
1.4 | Sensitivity Analysis | Downside resilience | CFO | High | Open |  | Price and steel shocks | 1.4
1.4 | Capacity Ramp-Up Plan | Operational throughput plan | Operations | Medium | Open |  | 40% to 95% | 1.4
1.4 | Energy Savings Analysis | Solar effect on opex | Engineering | Medium | Open |  | 20-30% energy savings | 1.4
1.5 | National Strategic Alignment Report | Usklađenost sa državnim ciljevima | Management | High | Open |  | Industrial and regional relevance | 1.5
1.5 | EU Policy Alignment Matrix | Green Deal / Chapter 20 / Taxonomy map | CFO / Consultant | High | Open |  | Grant and policy narrative | 1.5
1.5 | ESG Strategy Plan | Održivost i dekarbonizacija | ESG Team | High | Open |  | Solar and green manufacturing | 1.5
1.5 | Economic Impact Study | Multiplikator efekti | CFO / Economist | Medium | Open |  | Jobs and suppliers | 1.5
1.5 | Supply Chain Localization Plan | Lokalni dobavljači | Procurement | Medium | Open |  | 30-40 supplier target | 1.5
1.5 | Workforce Development Plan | Obuka kadra | HR Manager | Medium | Open |  | Skills ecosystem | 1.5
1.5 | Regional Development Impact | Doprinos regionu | Management | Medium | Open |  | Tuzi / Podgorica / wider CG | 1.5
1.5 | Grant Justification Document | Argumentacija za fondove | CFO | High | Open |  | National + EU policy fit | 1.5
2.1 | National Industrial Impact Report | Doprinos industriji CG | Management | High | Open |  | Structural diversification narrative | 2.1
2.1 | Import Substitution Analysis | Smanjenje uvoza | CFO / Economist | Medium | Open |  | Value-added industrial logic | 2.1
2.1 | Technology Transfer Plan | Industry 4.0 implementacija | Technical Director | Medium | Open |  | OEM / spillover path | 2.1
2.1 | Human Capital Strategy | Razvoj radne snage | HR Manager | High | Open |  | Training and retention | 2.1
2.1 | Local Supply Chain Plan | Lokalni dobavljači | Procurement | Medium | Open |  | Domestic industrial linkages | 2.1
2.1 | Economic Multiplier Study | Efekti na ekonomiju | CFO | Medium | Open |  | 1.5x-2.0x multiplier claim | 2.1
2.1 | Fiscal Contribution Analysis | Doprinos budžetu | CFO | High | Open |  | Tax and payroll benefits | 2.1
2.1 | Institutional Alignment Document | Industrial Policy 2024-2028 fit | Management | High | Open |  | State support logic | 2.1
2.2 | Energy Infrastructure Alignment Report | Usklađenost sa energetskim potrebama | Management | High | Open |  | Grid bottleneck narrative | 2.2
2.2 | Smart Grid Compatibility Study | Tehnička kompatibilnost | Technical Director | High | Open |  | Digital / bidirectional flow | 2.2
2.2 | Technical Specification Document | Standardi i performanse | Engineering | High | Open |  | 420 kV, C5-M, EC8 etc | 2.2
2.2 | Market Demand Forecast | Potražnja transformatora | Sales / Strategy | Medium | Open |  | Grid investment pull | 2.2
2.2 | Infrastructure Justification | Argumentacija investicije | CFO | High | Open |  | Low-risk demand platform | 2.2
2.2 | Regulatory Framework Analysis | TSO/DSO regulativa | CFO / Consultant | Medium | Open |  | Regulated investment pull | 2.2
2.2 | Contra-Cyclical Assessment | Otpornost industrije | CFO | Medium | Open |  | Demand resilience in downturn | 2.2
2.2 | Grant Eligibility Report | Kvalifikacija za fondove | CFO | High | Open |  | Energy transition alignment | 2.2
2.3 | Export Strategy Plan | Strategija izvoza | Sales Director | High | Open |  | 80% EU-focused exports | 2.3
2.3 | Logistics Analysis EU | Logističke rute i troškovi | Operations | Medium | Open |  | Transit and transport logic | 2.3
2.3 | OEM Partnership Framework | Partnerstva sa OEM | Management | High | Open |  | Backlog and quality integration | 2.3
2.3 | FX Risk Management Statement | Valutna stabilnost | CFO | Medium | Open |  | Natural EUR hedge | 2.3
2.3 | Global Value Chain Plan | Integracija u lance | Sales / Strategy | High | Open |  | OEM global standards | 2.3
2.3 | Industrial Spillover Study | Efekti na industriju CG | Management | Medium | Open |  | Reputational and skills spillover | 2.3
2.3 | Brand Strategy 'Made in Montenegro' | Reputacioni efekat | Marketing | Medium | Open |  | Industrial branding | 2.3
2.3 | Corporate Governance & Legal Compliance Document | Pravni okvir | CFO / Legal | High | Open |  | DOO, law and IFRS framing | 2.3
3.1 | Corporate Governance Framework | Upravljanje kompanijom | CFO / Legal | High | Open |  | Governance baseline | 3.1
3.1 | IFRS Accounting Policy | Finansijsko izvještavanje | CFO | High | Open |  | Accounting and reporting | 3.1
3.1 | UBO Ownership Document | Vlasnička transparentnost | Legal | High | Open |  | UBO disclosure | 3.1
3.1 | AML Compliance Policy | Regulatorna usklađenost | Compliance Officer | Medium | Open |  | AML/CFT | 3.1
3.1 | Anti-Corruption Policy | Reputaciona sigurnost | Management | High | Open |  | Conflict / related-party controls | 3.1
3.1 | Shareholder Agreement | Uređenje odnosa vlasnika | Legal | High | Open |  | Rights and exits | 3.1
3.1 | Capital Structure Plan | Privlačenje investitora | CFO | High | Open |  | Flexible instruments | 3.1
3.1 | Exit Strategy Framework | Buduća prodaja / transition | CFO / Management | Medium | Open |  | 7-10y optionality | 3.1
3.1 | Internal Control Manual | Operativna kontrola | CFO | Medium | Open |  | Control environment | 3.1
3.2 | Corporate Governance Charter | Struktura upravljanja | Management / Legal | High | Open |  | Two-tier governance | 3.2
3.2 | Board Structure Document | Organizacija odbora | Legal | High | Open |  | Board / committees | 3.2
3.2 | Shareholder Decision Framework | Prava vlasnika | Legal | Medium | Open |  | Reserved matters | 3.2
3.2 | Management Responsibility Matrix | Uloge menadžmenta | HR / Management | Medium | Open |  | Operational accountability | 3.2
3.2 | CFO Control Framework | Finansijska kontrola | CFO | High | Open |  | Budget veto | 3.2
3.2 | Investment Approval Policy | Odobrenje CAPEX-a | CFO / Board | High | Open |  | >500k threshold | 3.2
3.2 | ESG Governance Framework | ESG upravljanje | ESG Committee | High | Open |  | Grant and sustainability oversight | 3.2
3.2 | Management Incentive Policy | Bonus struktura | HR / CFO | Medium | Open |  | Performance-linked rewards | 3.2
3.2 | Delegation of Authority Matrix | Nivo odlučivanja | CFO | High | Open |  | Decision rights map | 3.2
3.3 | CFO Control Framework Manual | Finansijska kontrola | CFO | High | Open |  | Guardian model | 3.3
3.3 | CAPEX Approval Policy | Odobrenje investicija | CFO / Board | High | Open |  | Milestone based | 3.3
3.3 | Rolling Cash Flow Methodology | Likvidnost | CFO | High | Open |  | 13-week forecast | 3.3
3.3 | Working Capital Policy | Upravljanje kapitalom | CFO | Medium | Open |  | CCC control | 3.3
3.3 | Financial Covenants Monitoring | Praćenje bankarskih uslova | CFO | High | Open |  | DSCR etc | 3.3
3.3 | Procurement Policy | Nabavka i tenderi | Procurement | High | Open |  | 3 quotes >10k | 3.3
3.3 | Reporting Framework | System izvještavanja | CFO | High | Open |  | Weekly/monthly/quarterly packs | 3.3
3.3 | ERP Implementation Plan | Softverska integracija | IT / CFO | Medium | Open |  | Dynamics/Odoo concept | 3.3
3.3 | Budget Control Procedure | Kontrola troškova | CFO | High | Open |  | Budget vs actual | 3.3

## Task_Register
Task Register
Master control structure aligned to user canonical project-task format
Lifecycle_Activity | Phase | Step_ID | Step_Name | Detailed_Description | Responsible_Function | Dependency | Required_Evidence | Document_Type | Budget_EUR | Financial_Classification | Risk_Score_1_5 | Risk_Level | RAG_Status | Hard_Gate | Status | Institution | Contact_Person | Case_Number | Start_Date | Statutory_Deadline | Last_Update | Next_Action | Notes
Business Plan Harmonization | 1.1 | 1.1-T01 | Define detailed production ramp-up plan | Translate 10,000 t/year objective into annual/monthly ramp-up and utilization bridge | Technical Director | Ramp-up assumptions | Ramp-up memo | Planning Memo | 0 | OPEX/COGS planning | 4 | High | Amber | No | Not Started | [6 empty] | Build annual Y1-Y5 production table and utilization assumptions | Source 1.1
Business Plan Harmonization | 1.1 | 1.1-T02 | Prepare Tuzi location and logistics analysis | Document road/rail/port/airport advantages for investors and lenders | Project Development Team |  | Location analysis | Report | 0 | None | 3 | Medium | Amber | No | Not Started | [6 empty] | Validate every claimed transit advantage with source evidence | Source 1.1
Business Plan Harmonization | 1.1 | 1.1-T03 | Design 1 MWp solar integration concept | Define capex, expected output, self-consumption, savings sensitivity and grid interface | Engineering |  | Solar concept note | Technical study | 0 | CAPEX | 4 | High | Amber | No | Not Started | [6 empty] | Convert 20-30% savings statement into model-backed case | Source 1.1
Business Plan Harmonization | 1.1 | 1.1-T04 | Map DACH OEM target list | Create prioritized OEM outreach list and qualification criteria | Sales Director |  | Target account list | CRM / target list | 0 | OPEX | 4 | High | Amber | No | Not Started | [6 empty] | Separate primary DACH from secondary Balkan market | Source 1.1
Business Plan Harmonization | 1.1 | 1.1-T05 | Build ISO certification roadmap | Define timing, owners, external support and cost for ISO 9001/14001/45001 | Quality Manager |  | Certification roadmap | Plan | 0 | OPEX | 3 | Medium | Amber | No | Not Started | [6 empty] | Certification required before high-tier tenders | Source 1.1
Business Plan Harmonization | 1.2 | 1.2-T01 | Finalize funding structure | Lock debt / equity / grant / subordinated stack and approvals | CFO |  | Signed term sheets | Funding pack | 0 | Funding | 5 | High | Red | Yes | In Progress | [6 empty] | Confirm sources match total uses exactly | Source 1.2
Business Plan Harmonization | 1.2 | 1.2-T02 | Negotiate bank financing | Advance credit approval and covenant package | Management / CFO |  | Bank term sheet | Loan package | 0 | Funding | 5 | High | Red | Yes | In Progress | [6 empty] | Need grace period and DSCR-aligned amortization | Source 1.2
Business Plan Harmonization | 1.2 | 1.2-T03 | Prepare EU grant applications | Translate strategic narrative into eligible grant workstreams | CFO / Consultant |  | Grant application | Grant dossier | 0 | Funding | 4 | High | Amber | Yes | Not Started | [6 empty] | Eligibility and co-financing rules must be evidenced | Source 1.2
Business Plan Harmonization | 1.2 | 1.2-T04 | Build working capital model | Model inventory, receivables and payables for ramp-up period | CFO |  | WC model | Model | 0 | Working Capital | 4 | High | Amber | No | Not Started | [6 empty] | Link DSO 60-90 days to cash need | Source 1.2
Business Plan Harmonization | 1.2 | 1.2-T05 | Define contingency draw rules | Set authority, triggers and documentation for reserve use | CFO |  | Contingency policy | Policy | 0 | CAPEX | 3 | Medium | Amber | No | Not Started | [6 empty] | Reserve currently only 3.2% of uses | Source 1.2
Business Plan Harmonization | 1.3 | 1.3-T01 | Build EU transformer market map | Quantify gap, demand and target customer clusters | Sales Director |  | Market map | Market study | 0 | OPEX | 4 | High | Amber | No | Not Started | [6 empty] | Replace narrative with evidence-backed TAM/SAM/SOM | Source 1.3
Business Plan Harmonization | 1.3 | 1.3-T02 | Identify OEM target accounts | Prioritize Siemens/ABB/Schneider/Hitachi and tier-2 OEMs | Sales Team |  | Target list | CRM | 0 | OPEX | 4 | High | Amber | No | Not Started | [6 empty] | Separate strategic and transactional accounts | Source 1.3
Business Plan Harmonization | 1.3 | 1.3-T03 | Draft steel index-linked pricing policy | Translate CRU/HRC logic into contract clauses | CFO / Sales |  | Pricing template | Contract template | 0 | COGS | 5 | High | Red | No | Not Started | [6 empty] | Avoid unsupported 'margin protected' claims without test cases | Source 1.3
Business Plan Harmonization | 1.3 | 1.3-T04 | Prepare EN 1090 qualification path | Map requirements for weld and structural compliance | Quality Manager |  | Compliance checklist | Plan | 0 | OPEX | 4 | High | Amber | No | Not Started | [6 empty] | Mandatory for tender credibility | Source 1.3
Business Plan Harmonization | 1.3 | 1.3-T05 | Set steel price monitoring process | Create CRU/HRC watchlist and review cadence | Procurement |  | Index log | Procedure | 0 | COGS | 3 | Medium | Amber | No | Not Started | [6 empty] | Need nominated data source and approval rules | Source 1.3
Business Plan Harmonization | 1.4 | 1.4-T01 | Finalize 2026-2029 integrated model | Reconcile revenue, EBITDA, debt service and cash flow assumptions | CFO |  | Integrated model | Financial model | 0 | Financial model | 5 | High | Red | Yes | In Progress | [6 empty] | Current narrative needs full support schedule by year/month | Source 1.4
Business Plan Harmonization | 1.4 | 1.4-T02 | Prepare DSCR covenant model | Calculate DSCR under base and downside cases | CFO |  | DSCR schedule | Debt model | 0 | Debt | 5 | High | Red | Yes | In Progress | [6 empty] | Y2/Y3 threshold timing inconsistent across chapters | Source 1.4
Business Plan Harmonization | 1.4 | 1.4-T03 | Build NPV / IRR / payback file | Support return claims with model outputs and assumptions | CFO |  | Valuation model | Model | 0 | Valuation | 5 | High | Red | Yes | Not Started | [6 empty] | Payback wording must align with operating vs calendar years | Source 1.4
Business Plan Harmonization | 1.4 | 1.4-T04 | Lock utilization ramp assumptions | Translate 40/75/90/95% into tonnage and staffing requirements | Operations |  | Operations plan | Operations model | 0 | OPEX/COGS | 4 | High | Amber | No | Not Started | [6 empty] | Model should reconcile with 10,000 t capacity | Source 1.4
Business Plan Harmonization | 1.4 | 1.4-T05 | Run downside sensitivity tests | Test -15% price, +10% steel, volume shortfall, delay and grant shortfall | CFO |  | Sensitivity pack | Model | 0 | Risk | 5 | High | Red | No | Not Started | [6 empty] | Current downside cases too narrow for bank-grade stress | Source 1.4
Business Plan Harmonization | 1.5 | 1.5-T01 | Prepare EU policy alignment matrix | Map each claim to legal / policy source and project feature | CFO / Consultant |  | Policy matrix | Matrix | 0 | Grant | 5 | High | Red | Yes | Not Started | [6 empty] | Current draft contains uncited policy references | Source 1.5
Business Plan Harmonization | 1.5 | 1.5-T02 | Draft ESG and decarbonization strategy | Quantify emissions, solar benefits and taxonomy logic | ESG Manager |  | ESG plan | Strategy | 0 | ESG | 4 | High | Amber | No | Not Started | [6 empty] | Replace general ESG claims with measurable KPIs | Source 1.5
Business Plan Harmonization | 1.5 | 1.5-T03 | Map local supplier development program | Define onboarding criteria for 30-40 suppliers | Procurement |  | Supplier program | Plan | 0 | COGS/OPEX | 3 | Medium | Amber | No | Not Started | [6 empty] | Need realistic local capability mapping | Source 1.5
Business Plan Harmonization | 1.5 | 1.5-T04 | Define education center concept | Specify curriculum, partners, capex and opex | HR Manager |  | Training concept | Concept note | 0 | CAPEX/OPEX | 3 | Medium | Amber | No | Not Started | [6 empty] | Training center currently a concept only | Source 1.5
Business Plan Harmonization | 1.5 | 1.5-T05 | Build national impact case for government | Translate jobs/suppliers/exports into ministerial talking points | Management |  | Impact memo | Memo | 0 | None | 4 | High | Amber | No | Not Started | [6 empty] | Use verified macro assumptions only | Source 1.5
Business Plan Harmonization | 2.1 | 2.1-T01 | Write industrial impact analysis | Back structural diversification claims with CG macro data | CFO |  | Industrial impact report | Report | 0 | None | 5 | High | Red | No | Not Started | [6 empty] | Tourism / manufacturing GDP shares need source and consistency | Source 2.1
Business Plan Harmonization | 2.1 | 2.1-T02 | Map domestic supplier base | Identify realistic local subcontractor capabilities | Procurement |  | Supplier mapping | Database | 0 | COGS | 3 | Medium | Amber | No | Not Started | [6 empty] | Avoid counting suppliers with no technical fit | Source 2.1
Business Plan Harmonization | 2.1 | 2.1-T03 | Establish university / school partnerships | Define cooperation with UCG and technical schools | HR / Management |  | MoU drafts | MoU | 0 | OPEX | 3 | Medium | Amber | No | Not Started | [6 empty] | Need partner commitment evidence | Source 2.1
Business Plan Harmonization | 2.1 | 2.1-T04 | Draft Industry 4.0 roadmap | Translate spillover claims into equipment / process roadmap | Technical Director |  | Roadmap | Roadmap | 0 | CAPEX | 4 | High | Amber | No | Not Started | [6 empty] | Spillover should be tied to training and supplier interfaces | Source 2.1
Business Plan Harmonization | 2.1 | 2.1-T05 | Quantify fiscal contribution | Model VAT/CIT/payroll and net budget effect | CFO |  | Fiscal model | Model | 0 | Tax | 4 | High | Amber | No | Not Started | [6 empty] | Use conservative revenue and payroll assumptions | Source 2.1
Business Plan Harmonization | 2.2 | 2.2-T01 | Analyze smart grid requirements | Translate market need into product specification set | Engineering |  | Spec matrix | Technical matrix | 0 | CAPEX/OPEX | 4 | High | Amber | No | Not Started | [6 empty] | Need hard link between tank design and smart-grid requirement | Source 2.2
Business Plan Harmonization | 2.2 | 2.2-T02 | Build technical product specification pack | Document corrosion, seismic and voltage requirements | Engineering |  | Product spec | Technical pack | 0 | CAPEX/COGS | 4 | High | Amber | No | Not Started | [6 empty] | Claims need supporting standards and design calculations | Source 2.2
Business Plan Harmonization | 2.2 | 2.2-T03 | Track EU grid investment pipeline | Map TSO/DSO programs and demand drivers | Strategy Team |  | Pipeline tracker | Tracker | 0 | Sales | 4 | High | Amber | No | Not Started | [6 empty] | Numbers like €584bn and €170bn must be cited | Source 2.2
Business Plan Harmonization | 2.2 | 2.2-T04 | Map TSO/DSO and OEM target projects | Create opportunity list tied to infrastructure spending | Sales |  | Target pipeline | CRM | 0 | Sales | 4 | High | Amber | No | Not Started | [6 empty] | Need project-level opportunity evidence | Source 2.2
Business Plan Harmonization | 2.2 | 2.2-T05 | Prepare energy-transition grant narrative | Align project to resilience / smart grid funding criteria | CFO |  | Grant memo | Memo | 0 | Grant | 4 | High | Amber | No | Not Started | [6 empty] | Distinguish public utility demand from private OEM sales path | Source 2.2
Business Plan Harmonization | 2.3 | 2.3-T01 | Define EU export strategy | Prioritize DACH and Italy with route-to-market logic | Sales Director |  | Export strategy | Plan | 0 | Revenue | 4 | High | Amber | No | Not Started | [6 empty] | Need customer-level evidence not only geography | Source 2.3
Business Plan Harmonization | 2.3 | 2.3-T02 | Build logistics route model | Translate transit claims into cost, days and incoterm model | Operations |  | Route model | Model | 0 | COGS | 4 | High | Amber | No | Not Started | [6 empty] | Transit claims should reconcile with chosen transport mode | Source 2.3
Business Plan Harmonization | 2.3 | 2.3-T03 | Negotiate OEM frame agreements | Convert partnership narrative into pipeline milestones | Management |  | Negotiation tracker | Tracker | 0 | Revenue | 5 | High | Red | No | Not Started | [6 empty] | Backlog assumptions unsupported until signed LOI/term sheet | Source 2.3
Business Plan Harmonization | 2.3 | 2.3-T04 | Document natural FX hedge policy | Show currency matching between debt and revenue | CFO |  | Treasury note | Policy | 0 | Funding | 3 | Medium | Amber | No | Not Started | [6 empty] | Still test for non-EUR supplier exposure | Source 2.3
Business Plan Harmonization | 2.3 | 2.3-T05 | Implement IFRS and governance setup | Translate legal narrative into corporate documents | CFO / Legal |  | Policies and resolutions | Governance pack | 0 | OPEX | 4 | High | Amber | No | Not Started | [6 empty] | Legal structure claims need registration evidence | Source 2.3
Business Plan Harmonization | 3.1 | 3.1-T01 | Implement IFRS accounting framework | Adopt accounting policy manual and reporting timetable | CFO |  | IFRS manual | Policy | 0 | OPEX | 4 | High | Amber | No | Not Started | [6 empty] | Need accounting policy and audit readiness evidence | Source 3.1
Business Plan Harmonization | 3.1 | 3.1-T02 | Complete UBO registration package | Validate all ultimate beneficial owner filings | Legal |  | CRPS / UBO filings | Filing pack | 0 | Compliance | 5 | High | Red | Yes | Not Started | [6 empty] | Critical for KYC and banking | Source 3.1
Business Plan Harmonization | 3.1 | 3.1-T03 | Draft flexible charter / statute | Provide capital flexibility and conversion rights framework | Legal |  | Statute draft | Corporate document | 0 | Legal | 4 | High | Amber | No | Not Started | [6 empty] | Legal permissibility of share classes in DOO must be checked | Source 3.1
Business Plan Harmonization | 3.1 | 3.1-T04 | Adopt anti-corruption and conflict rules | Implement related-party and conflict approval rules | Management |  | Policy set | Policy | 0 | Compliance | 4 | High | Amber | No | Not Started | [6 empty] | Statute alone may be insufficient; operational policy needed | Source 3.1
Business Plan Harmonization | 3.1 | 3.1-T05 | Prepare audit readiness plan | Sequence controls for Big4 / lender due diligence | CFO |  | Audit readiness plan | Plan | 0 | OPEX | 3 | Medium | Amber | No | Not Started | [6 empty] | Need evidence pack owner and timeline | Source 3.1
Business Plan Harmonization | 3.2 | 3.2-T01 | Constitute board structure | Define board members, terms and authority | Management |  | Board resolutions | Corporate resolution | 0 | Governance | 5 | High | Red | Yes | Not Started | [6 empty] | Independent experts and committee composition must be real, not conceptual | Source 3.2
Business Plan Harmonization | 3.2 | 3.2-T02 | Define ESG committee mandate | Set scope, KPIs and reporting cadence | Management |  | Committee charter | Charter | 0 | ESG | 4 | High | Amber | No | Not Started | [6 empty] | Need explicit overlap rules with board and management | Source 3.2
Business Plan Harmonization | 3.2 | 3.2-T03 | Issue CFO veto policy | Formalize budget overrun veto and escalation path | CFO |  | Control policy | Policy | 0 | Finance | 5 | High | Red | Yes | Not Started | [6 empty] | High-value lender comfort item | Source 3.2
Business Plan Harmonization | 3.2 | 3.2-T04 | Build management KPI and incentive plan | Tie bonuses to EBITDA / DSCR / ROI / ESG with calculation rules | HR / CFO |  | Incentive plan | Policy | 0 | OPEX | 4 | High | Amber | No | Not Started | [6 empty] | Avoid perverse incentives / short-termism | Source 3.2
Business Plan Harmonization | 3.2 | 3.2-T05 | Publish decision-rights matrix | Separate strategy / capex / operations / finance / ESG approvals | CFO |  | DoA matrix | Matrix | 0 | Governance | 4 | High | Amber | No | Not Started | [6 empty] | Needs thresholds and emergency override logic | Source 3.2
Business Plan Harmonization | 3.3 | 3.3-T01 | Implement 13-week rolling cash flow | Set weekly cadence, responsibility and variance bridge | CFO |  | 13-week model | Cash flow model | 0 | Liquidity | 5 | High | Red | Yes | In Progress | [6 empty] | Core control stack item; no slippage tolerated | Source 3.3
Business Plan Harmonization | 3.3 | 3.3-T02 | Build milestone-based CAPEX payment control | Require physical milestone evidence and dual sign-off | CFO / PM |  | Milestone register | Control file | 0 | CAPEX | 5 | High | Red | Yes | In Progress | [6 empty] | Must integrate with contracts and engineer certification | Source 3.3
Business Plan Harmonization | 3.3 | 3.3-T03 | Automate covenant monitoring | Set DSCR / D:E / EBITDA:Interest triggers and alerts | CFO |  | Covenant tracker | Dashboard | 0 | Debt | 5 | High | Red | Yes | Not Started | [6 empty] | Need exact calculation definitions from financing docs | Source 3.3
Business Plan Harmonization | 3.3 | 3.3-T04 | Implement 3-bid procurement rule | Create tender record and exception approval process | Procurement |  | Bid log | Procedure | 0 | Procurement | 4 | High | Amber | No | Not Started | [6 empty] | Need exception handling for sole-source procurement | Source 3.3
Business Plan Harmonization | 3.3 | 3.3-T05 | Select and implement ERP | Choose ERP and define phased rollout | IT / CFO |  | ERP selection paper | Implementation plan | 0 | CAPEX/OPEX | 4 | High | Amber | No | Not Started | [6 empty] | Avoid over-claiming real-time integration before go-live | Source 3.3
Business Plan Harmonization | 3.3 | 3.3-T06 | Launch weekly flash and monthly pack | Define templates and review cadence | CFO |  | Reporting templates | Template pack | 0 | OPEX | 4 | High | Amber | No | Not Started | [6 empty] | Each pack needs source data owner | Source 3.3
Business Plan Harmonization | 3.3 | 3.3-T07 | Set inventory and CCC dashboard | Track steel, components and cash conversion cycle | Operations / CFO |  | Inventory dashboard | Dashboard | 0 | Working Capital | 4 | High | Amber | No | Not Started | [6 empty] | Daily monitoring claim needs system capability | Source 3.3

## Financial_Map
Financial Map
Where each chapter affects CAPEX, OPEX, COGS, Funding, Revenue or KPI logic
Chapter | Category | Subcategory | Type | Amount_or_Value | Status | Funding_Source | Comment | Source_Section
1.1 | Production plant | Building and core production infrastructure | CAPEX |  |  |  | Base industrial facility | 1.1
1.1 | Production equipment | CNC machines | CAPEX |  |  |  | Precision metal processing | 1.1
1.1 | Automation | Robotic welding | CAPEX |  |  |  | COGS optimization driver | 1.1
1.1 | Energy system | 1 MWp solar plant | CAPEX |  |  |  | OPEX reduction driver | 1.1
1.1 | Certification | ISO implementation | OPEX |  |  |  | Market-access cost | 1.1
1.1 | Energy | Electricity consumption | OPEX |  |  |  | Target 20-30% saving claim requires model | 1.1
1.1 | Labor | Operators and engineers | OPEX |  |  |  | Ramp-up staffing | 1.1
1.1 | Maintenance | Equipment service | OPEX |  |  |  | Recurring technical upkeep | 1.1
1.1 | Materials | Steel and components | COGS |  |  |  | Primary direct cost | 1.1
1.1 | Logistics | Transport and delivery | COGS |  |  |  | Export delivery cost | 1.1
1.2 | Equity | Sponsor equity | Funding | 1800000 | Secured |  | 17.5% | 1.2
1.2 | Bank Debt | Senior financing | Funding | 4800000 | In approval |  | 46.5% | 1.2
1.2 | EU Grants | Development and EU grants | Funding | 2400000 | Under evaluation |  | 23.2% | 1.2
1.2 | Subordinated Capital | Sub debt/additional investor equity | Funding | 1330000 | Negotiation |  | 12.8% | 1.2
1.2 | CAPEX | Project design/build/machinery/solar | Use | 8000000 |  |  |  | 1.2
1.2 | Working Capital | Startup liquidity and raw materials | Use | 2000000 |  |  |  | 1.2
1.2 | Contingency | Reserve | Use | 330000 |  |  |  | 1.2
1.3 | Raw materials | Steel | COGS |  |  |  | Primary margin driver | 1.3
1.3 | Transport | Export logistics | COGS |  |  |  | Near-shoring claim driver | 1.3
1.3 | Energy | Electricity | OPEX |  |  |  | Solar expected to reduce cost | 1.3
1.3 | Automation | Robotic welding | CAPEX |  |  |  | Labor and quality leverage | 1.3
1.3 | Quality | Traceability systems | CAPEX |  |  |  | Tender and OEM requirement | 1.3
1.3 | Sales | OEM partnership development | OPEX |  |  |  | Commercial setup cost | 1.3
1.3 | Tendering | Certification and prequalification | OPEX |  |  |  | Barrier-to-entry spend | 1.3
1.3 | Pricing | Index-linked contracts | Strategy |  |  |  | Margin protection logic | 1.3
1.4 | 2026 Revenue | Y1 | Revenue | 8800000 |  |  | 40% utilization | 1.4
1.4 | 2027 Revenue | Y2 | Revenue | 16500000 |  |  | 75% utilization | 1.4
1.4 | 2028 Revenue | Y3 | Revenue | 19800000 |  |  | 90% utilization | 1.4
1.4 | 2029 Revenue | Y4 | Revenue | 20900000 |  |  | 95% utilization | 1.4
1.4 | 2026 EBITDA Margin | Y1 | KPI | 12% |  |  |  | 1.4
1.4 | 2027 EBITDA Margin | Y2 | KPI | 23% |  |  |  | 1.4
1.4 | 2028 EBITDA Margin | Y3 | KPI | 25% |  |  |  | 1.4
1.4 | 2029 EBITDA Margin | Y4 | KPI | 26% |  |  |  | 1.4
1.4 | 2026 DSCR | Y1 | KPI | 90% |  |  |  | 1.4
1.4 | 2027 DSCR | Y2 | KPI | 1.4 |  |  |  | 1.4
1.4 | 2028 DSCR | Y3 | KPI | 1.6 |  |  |  | 1.4
1.4 | 2029 DSCR | Y4 | KPI | 1.8 |  |  |  | 1.4
1.5 | Solar plant | Energy system | CAPEX |  |  |  | Green manufacturing anchor | 1.5
1.5 | ESG systems | Monitoring and reporting | CAPEX |  |  |  | Taxonomy / grant readiness | 1.5
1.5 | Training | Workforce development | OPEX |  |  |  | Recurring skill-building cost | 1.5
1.5 | Certification | Standards and audits | OPEX |  |  |  | Market-access and grant support | 1.5
1.5 | Local supplier setup | Localization support | COGS/OPEX |  |  |  | Potential supplier development spend | 1.5
1.5 | Grant access | EU funds | Funding |  |  |  | Potential WACC reduction | 1.5
2.1 | Industry 4.0 systems | Automation / IoT / digital quality | CAPEX |  |  |  | Productivity and traceability | 2.1
2.1 | Training center | Education capability | CAPEX |  |  |  | Human capital asset | 2.1
2.1 | Employee training | Skills development | OPEX |  |  |  | Recurring capability cost | 2.1
2.1 | Local subcontractors | Domestic outsourcing | COGS |  |  |  | Potentially lower logistics / higher agility | 2.1
2.1 | Export revenues | Industrial output | Revenue |  |  |  | Higher value-added exports | 2.1
2.1 | Fiscal contribution | Taxes and payroll | Macro |  |  |  | State budget benefit narrative | 2.1
2.2 | Specialized equipment | High-voltage compatible systems | CAPEX |  |  |  | Premium capability | 2.2
2.2 | Anti-corrosion systems | C5-M coating capability | CAPEX |  |  |  | Durability feature | 2.2
2.2 | Digital monitoring | Traceability / monitoring | CAPEX |  |  |  | Smart-grid compatibility claim | 2.2
2.2 | Certification | Standards / audit | OPEX |  |  |  | Tender entry cost | 2.2
2.2 | Materials | Special steel | COGS |  |  |  | Quality/performance | 2.2
2.2 | Coatings | Protective systems | COGS |  |  |  | Product durability | 2.2
2.2 | Grant access | Energy-transition funds | Funding |  |  |  | Potential cost of capital reduction | 2.2
2.2 | Stable demand | Energy infrastructure spending | Revenue |  |  |  | Lower cyclicality | 2.2
2.3 | EU exports | Sales to EU customers | Revenue |  |  |  | 80% target | 2.3
2.3 | Transport | Outbound logistics | COGS |  |  |  | Transit cost | 2.3
2.3 | Lean supply benefit | Lower customer inventory | Strategy |  |  |  | Commercial selling point | 2.3
2.3 | OEM agreements | Backlog stability | Revenue |  |  |  | Not bankable until evidenced | 2.3
2.3 | FX natural hedge | EUR revenues vs EUR debt | Finance |  |  |  | Reduced currency mismatch | 2.3
2.3 | Governance | Compliance / reporting | OPEX |  |  |  | IFRS and legal readiness | 2.3
2.3 | Certification | Standards | OPEX |  |  |  | Market access | 2.3
3.1 | Audit | Big4 or equivalent review | OPEX |  |  |  | Audit readiness cost | 3.1
3.1 | Compliance | AML / governance | OPEX |  |  |  | Policy and monitoring cost | 3.1
3.1 | Legal services | Statute / agreements | OPEX |  |  |  | Corporate structuring cost | 3.1
3.1 | IFRS implementation | Reporting setup | OPEX |  |  |  | Accounting transition cost | 3.1
3.1 | Governance systems | Controls | OPEX |  |  |  | Operating control environment | 3.1
3.1 | Investor capital | Equity access | Funding |  |  |  | Governance enables funding access | 3.1
3.2 | Board costs | Board and committee fees | OPEX |  |  |  | Governance cost | 3.2
3.2 | ESG committee | Oversight cost | OPEX |  |  |  | Grant/funding readiness | 3.2
3.2 | Management bonus | Performance incentives | OPEX |  |  |  | Variable comp | 3.2
3.2 | Governance systems | Controls and reporting | OPEX |  |  |  | Control discipline | 3.2
3.2 | CFO control | Budget protection | Finance |  |  |  | Risk-reduction mechanism | 3.2
3.2 | Investor capital | Funding access | Funding |  |  |  | Governance premium | 3.2
3.3 | ERP system | Software / implementation | CAPEX |  |  |  | Digital control infrastructure | 3.3
3.3 | IT integration | Systems setup | CAPEX |  |  |  | Implementation effort | 3.3
3.3 | ERP licenses | Annual subscription / maintenance | OPEX |  |  |  | Recurring software cost | 3.3
3.3 | Finance team | CFO control function | OPEX |  |  |  | Control cost | 3.3
3.3 | Procurement system | Tender process support | OPEX |  |  |  | Transparency and savings | 3.3
3.3 | Cash flow monitoring | Liquidity management | Finance |  |  |  | Risk reduction | 3.3
3.3 | Covenant monitoring | Debt compliance | Finance |  |  |  | Bankability support | 3.3

## Strategy_OKR
Strategy & OKR
Harmonized strategic goals and measurable outcomes extracted from the text
Chapter | Strategic_Goal | Key_Result | Owner | Timeline | Status_% | Forensic_Note | Source_Section
1.1 | Reach full production scale | Achieve 10,000 t/year by Year 5 | Operations Director | Y5 | 0% | Set measurable baseline before external use | 1.1
1.1 | Reduce energy cost exposure | Commission 1 MWp solar system | Engineering | Y2/Y3 | 0% | Set measurable baseline before external use | 1.1
1.1 | Maintain credit quality | DSCR above 1.25 after ramp-up | CFO | Y2/Y3 | 0% | Set measurable baseline before external use | 1.1
1.1 | Achieve investment return | ROI within 5 years of COD | CFO | Y5 | 0% | Set measurable baseline before external use | 1.1
1.1 | Win export position | Secure DACH OEM customer base | Sales Director | Y2/Y3 | 0% | Set measurable baseline before external use | 1.1
1.1 | Qualify for tenders | Obtain ISO 9001/14001/45001 | Quality Manager | Y1 | 0% | Set measurable baseline before external use | 1.1
1.2 | Close full financing package | Secure 10.33M total funding | CFO | Pre-FID | 0% | Set measurable baseline before external use | 1.2
1.2 | Lower WACC | Approve 2.4M grants | CFO | Pre-close | 0% | Set measurable baseline before external use | 1.2
1.2 | Protect debt service | Reach DSCR >1.25 | CFO | Y3 | 0% | Set measurable baseline before external use | 1.2
1.2 | Maintain liquidity | Fund 2.0M working capital buffer | CFO | Y1 | 0% | Set measurable baseline before external use | 1.2
1.2 | Preserve resilience without grants | Positive operating cash flow at 70-80% utilization | CFO | Y2/Y3 | 0% | Set measurable baseline before external use | 1.2
1.2 | Diversify capital sources | Debt + grant + equity + subordinated mix | Management | Pre-close | 0% | Set measurable baseline before external use | 1.2
1.3 | Exploit market gap | Secure 3 OEM partnerships | Sales Director | Y2 | 0% | Set measurable baseline before external use | 1.3
1.3 | Reduce logistics burden for customers | Achieve 15-25% lower transit cost / lead benefit vs overseas | Operations | Y2 | 0% | Set measurable baseline before external use | 1.3
1.3 | Protect gross margin | Implement index-linked pricing in contracts | CFO | Y1/Y2 | 0% | Set measurable baseline before external use | 1.3
1.3 | Enter EU tenders | Obtain EN 1090 / ISO qualification | Quality Manager | Y1/Y2 | 0% | Set measurable baseline before external use | 1.3
1.3 | Build stable backlog | Sign frame agreements | Sales Director | Y2/Y3 | 0% | Set measurable baseline before external use | 1.3
1.3 | Deliver fast | 3-7 day transit promise for target markets | Logistics Director | Y2 | 0% | Set measurable baseline before external use | 1.3
1.4 | Expand EBITDA margin | Reach 26% by Y4 | CFO | 2029 | 0% | Set measurable baseline before external use | 1.4
1.4 | Stabilize cash flow | Positive cumulative operating cash build by Y3 | CFO | 2028 | 0% | Set measurable baseline before external use | 1.4
1.4 | Service debt safely | Maintain DSCR >1.25 | CFO | 2027 onward | 0% | Set measurable baseline before external use | 1.4
1.4 | Optimize energy opex | Reduce energy cost via solar | Operations | 2027 onward | 0% | Set measurable baseline before external use | 1.4
1.4 | Recover invested capital | 5-year payback | CFO | 2030/2031 | 0% | Set measurable baseline before external use | 1.4
1.4 | Lift utilization | Reach 95% by Y4 | Operations | 2029 | 0% | Set measurable baseline before external use | 1.4
1.5 | Position as EU strategic partner | Enter EU supply chain narrative | Management | Ongoing | 0% | Set measurable baseline before external use | 1.5
1.5 | Win EU grants | Obtain grant approvals | CFO | Pre-close | 0% | Set measurable baseline before external use | 1.5
1.5 | Decarbonize production | Install 1 MW solar plant | Engineering | Y2 | 0% | Set measurable baseline before external use | 1.5
1.5 | Develop local supply chain | Engage 30+ suppliers | Procurement | Y2/Y3 | 0% | Set measurable baseline before external use | 1.5
1.5 | Develop workforce | Launch training center concept | HR | Y2 | 0% | Set measurable baseline before external use | 1.5
1.5 | Support regional development | Create 50+ direct jobs | Management | Y1-Y4 | 0% | Set measurable baseline before external use | 1.5
1.5 | Meet ESG alignment | Document taxonomy compliance | ESG Manager | Y1/Y2 | 0% | Set measurable baseline before external use | 1.5
2.1 | Diversify CG industry | Launch export-oriented manufacturing platform | Management | Y1-Y2 | 0% | Set measurable baseline before external use | 2.1
2.1 | Increase value-added exports | Sell high-precision energy components | CFO / Sales | Y2 onward | 0% | Set measurable baseline before external use | 2.1
2.1 | Enable technology transfer | Implement Industry 4.0 stack | Technical Director | Y1-Y3 | 0% | Set measurable baseline before external use | 2.1
2.1 | Develop skills ecosystem | Launch training partnerships | HR Manager | Y1-Y2 | 0% | Set measurable baseline before external use | 2.1
2.1 | Build local supply chain | Activate 30+ suppliers | Procurement | Y2-Y3 | 0% | Set measurable baseline before external use | 2.1
2.1 | Generate fiscal contribution | Show positive budget impact | CFO | Y2 onward | 0% | Set measurable baseline before external use | 2.1
2.2 | Position in smart-grid chain | Win OEM / infrastructure demand linkage | Management | Y2 | 0% | Set measurable baseline before external use | 2.2
2.2 | Build technical superiority | Meet EN/ISO / technical specifications | Quality Manager | Y1/Y2 | 0% | Set measurable baseline before external use | 2.2
2.2 | Secure stable demand | Win long-term agreements | Sales | Y2/Y3 | 0% | Set measurable baseline before external use | 2.2
2.2 | Protect downside | Anchor project in critical infrastructure demand | CFO | Ongoing | 0% | Set measurable baseline before external use | 2.2
2.2 | Access energy-transition capital | Obtain EU/public support | CFO | Pre-close | 0% | Set measurable baseline before external use | 2.2
2.2 | Qualify with regulated buyers | Meet TSO/DSO relevant standards | Technical Director | Y2 | 0% | Set measurable baseline before external use | 2.2
2.3 | Run export-led model | Export >80% of output | Sales Director | Y2 onward | 0% | Set measurable baseline before external use | 2.3
2.3 | Integrate with OEMs | Sign frame agreements | Management | Y2/Y3 | 0% | Set measurable baseline before external use | 2.3
2.3 | Improve logistics speed | Deliver to EU in <5 days road lead times | Operations | Y2 | 0% | Set measurable baseline before external use | 2.3
2.3 | Reduce currency risk | Match EUR revenues with EUR debt | CFO | Immediate | 0% | Set measurable baseline before external use | 2.3
2.3 | Build country reputation | Export high-tech 'Made in Montenegro' products | Management | Y2 onward | 0% | Set measurable baseline before external use | 2.3
2.3 | Institutionalize governance | Implement IFRS and legal compliance | CFO | Y1 | 0% | Set measurable baseline before external use | 2.3
3.1 | Achieve financial transparency | Implement IFRS | CFO | Y1 | 0% | Set measurable baseline before external use | 3.1
3.1 | Enable investor readiness | Complete audit-ready environment | CFO | Y1/Y2 | 0% | Set measurable baseline before external use | 3.1
3.1 | Preserve capital flexibility | Adopt flexible statute | Legal | Y1 | 0% | Set measurable baseline before external use | 3.1
3.1 | Strengthen compliance | Adopt AML and anti-corruption controls | Management | Y1 | 0% | Set measurable baseline before external use | 3.1
3.1 | Maintain exit optionality | Keep structure exit-ready | CFO | Long term | 0% | Set measurable baseline before external use | 3.1
3.1 | Accelerate KYC | Maintain clean UBO record | Legal | Immediate | 0% | Set measurable baseline before external use | 3.1
3.2 | Enforce financial discipline | Zero unauthorized spend | CFO | Immediate/Ongoing | 0% | Set measurable baseline before external use | 3.2
3.2 | Run professional management model | Performance-linked KPIs active | CEO / HR | Y1 | 0% | Set measurable baseline before external use | 3.2
3.2 | Institutionalize ESG governance | ESG committee operational | Board | Y1 | 0% | Set measurable baseline before external use | 3.2
3.2 | Protect investor capital | Formal governance implemented | Management | Y1 | 0% | Set measurable baseline before external use | 3.2
3.2 | Control capex approvals | All >500k investments formally approved | CFO / Board | Ongoing | 0% | Set measurable baseline before external use | 3.2
3.2 | Clarify accountability | Decision matrix implemented | CFO | Immediate | 0% | Set measurable baseline before external use | 3.2
3.3 | Preserve liquidity | 13-week forecast active | CFO | Immediate | 0% | Set measurable baseline before external use | 3.3
3.3 | Eliminate capex leakage | Zero payments without milestone sign-off | CFO | Immediate | 0% | Set measurable baseline before external use | 3.3
3.3 | Protect covenants | No covenant breach | CFO | Ongoing | 0% | Set measurable baseline before external use | 3.3
3.3 | Optimize working capital | Improve CCC | CFO / Operations | Y1/Y2 | 0% | Set measurable baseline before external use | 3.3
3.3 | Ensure transparent procurement | 3-quote compliance live | Procurement | Immediate | 0% | Set measurable baseline before external use | 3.3
3.3 | Digitize controls | ERP selected and implemented | IT / CFO | Y1/Y2 | 0% | Set measurable baseline before external use | 3.3
3.3 | Accelerate correction cycle | Monthly budget vs actual review active | CFO | Immediate | 0% | Set measurable baseline before external use | 3.3

## Issue_Log
Forensic Issue Log
Exact clauses and cross-references that require correction, evidence, or narrative tightening before lender / investor use
Issue_Area | Source_Chapter_or_CrossRef | Issue_Title | Severity | Exact_Trigger_Text_or_Clause | Why_Flagged | Impact_Area | Owner | Resolution_Status | Required_Action
Cross-chapter | 1.5 vs 2.1 | Chapter 20 timing | High | 1.5 states "Chapter 20 ... provisionally closed in December 2024", while 2.1 states alignment with Chapter 20 "which Montenegro provisionally closed 2024/2025". | Internal contradiction on closure timing. Must use one verified date and cite the official source. | Legal / policy credibility | CFO / Legal / Strategy | Open | Correct text, attach evidence, and reconcile across workbook.
1.1 / 1.4 / 1.2 | 1.1, 1.2, 1.4 | DSCR timing inconsistency | High | 1.1 says DSCR above 1.25 after ramp-up "years 2-3"; 1.2 says DSCR exceeds 1.25 "by year 3"; 1.4 table shows DSCR 1.4x already in 2027 (Y2). | Debt-service narrative is not internally consistent. Align covenant achievement timing across all chapters. | Bankability / lender trust | CFO / Legal / Strategy | Open | Correct text, attach evidence, and reconcile across workbook.
1.5 | 1.5 | Regional geography wording | Medium | Text says Tuzi project "jača sjever i centralni dio Crne Gore", but Tuzi/Podgorica is not a northern location. | Geographic framing is imprecise and weakens institutional credibility. | Institutional narrative | Respective owner | Open | Correct text, attach evidence, and reconcile across workbook.
1.3 | 1.3 | Absolute claim without evidence | High | Phrase: "100% traceability (sa digitalnim testiranjem i nultim otpadom)". | Absolute claims ('100%', 'zero waste') require measurable system design and evidence. Otherwise remove or qualify. | Technical / ESG credibility | CFO / Legal / Strategy | Open | Correct text, attach evidence, and reconcile across workbook.
1.3 | 1.3 | Named customer assumption presented as fact | High | Lists Siemens Energy, ABB, Schneider Electric, Hitachi Energy as target OEM partners without any evidence of contact status, LOI, RFQ, NDA, or qualification stage. | Potential framing manipulation. Distinguish aspirational targets from active pipeline backed by evidence. | Commercial credibility | CFO / Legal / Strategy | Open | Correct text, attach evidence, and reconcile across workbook.
2.3 | 2.3 | Frame-agreement backlog overstatement | High | Claim: "dobijamo stabilan backlog kroz sticky ugovore (frame agreements)" before any signed agreement is disclosed. | Backlog cannot be treated as secured until evidenced by executed agreements or at least verifiable LOIs. | Revenue risk | CFO / Legal / Strategy | Open | Correct text, attach evidence, and reconcile across workbook.
1.4 | 1.4 | Return narrative ambiguity | Medium | States both "Payback Period: 5 years" and "kumulativni neto cash flow postaje pozitivan već u trećoj godini operativnog rada". | These can both be true, but the distinction between cumulative operating cash generation and full investment payback must be explicit. | Investor interpretation | Respective owner | Open | Correct text, attach evidence, and reconcile across workbook.
1.4 | 1.4 | Incomplete downside testing | High | Sensitivity mentions only 15% lower selling price or 10% higher steel cost. | Bank-grade downside testing should also include volume delay, ramp-up delay, capex overrun, grant shortfall, FX on imports, collection delays and interest-rate shocks. | Risk analysis sufficiency | CFO / Legal / Strategy | Open | Correct text, attach evidence, and reconcile across workbook.
1.2 | 1.2 | Contingency may be understated | High | Contingency fund = €0.33m on total uses of €10.33m and capex of €8.0m (~3.2% of total uses; ~4.1% of capex). | Narrative calls 3-5% standard, but contingency is at the low end and may be insufficient for greenfield industrial capex unless supported by quote maturity and risk register. | Capex adequacy | CFO / Legal / Strategy | Open | Correct text, attach evidence, and reconcile across workbook.
2.1 | 2.1 | Macro percentages need source discipline | High | Tourism "25-30% GDP" and manufacturing / industry "3-12% GDP" appear as wide unsupported ranges. | Ranges are too wide to be decision-useful and look unverified. Must be sourced and defined consistently (gross value added? direct + indirect? industry vs manufacturing?). | Macro credibility | CFO / Legal / Strategy | Open | Correct text, attach evidence, and reconcile across workbook.
2.2 | 2.2 | Infrastructure numbers uncited | High | Claims include EU plan "450 GW renewable by 2028", "EUR 584 billion to 2030", and "EUR 170 billion for digitalization/Smart Grids". | These are load-bearing figures and require explicit source citations and definitions. | Grant / lender diligence | CFO / Legal / Strategy | Open | Correct text, attach evidence, and reconcile across workbook.
1.3 | 1.3 | Price increase statistic uncited | High | Claim: transformer equipment prices increased "60-80% since 2020". | High-impact pricing claim requires source, basket definition and geography. | Market analysis | CFO / Legal / Strategy | Open | Correct text, attach evidence, and reconcile across workbook.
2.2 | 2.2 | Lead-time claim uncited | High | Lead times for large power transformers stated as 4-5 years and sometimes "to 2030". | Requires current evidence, date stamp and scope (Europe? specific OEMs? custom large power units?). | Demand thesis | CFO / Legal / Strategy | Open | Correct text, attach evidence, and reconcile across workbook.
3.1 | 3.1 | Legal flexibility claim may exceed DOO reality | High | Claim that the statute can enable "different classes of shares/units" and capital instruments in a DOO without complicated amendments. | This requires precise legal validation under the new law. Do not assume AD-like flexibility without article-level legal support. | Corporate law compliance | CFO / Legal / Strategy | Open | Correct text, attach evidence, and reconcile across workbook.
3.2 | 3.2 | Governance architecture may exceed actual setup | Medium | Board, independent members and ESG Committee are presented as if operational, but text does not show appointments, charters, or resolutions. | Conceptual governance must not be written as implemented governance until formally established. | Governance credibility | Respective owner | Open | Correct text, attach evidence, and reconcile across workbook.
3.3 | 3.3 | ERP overstatement risk | Medium | Narrative suggests real-time integrated ERP control while the system is only "planned". | Future-state software capability should be clearly separated from current-state controls. | Operational realism | Respective owner | Open | Correct text, attach evidence, and reconcile across workbook.
3.3 | 3.3 | Procurement rule missing exception logic | Medium | Rule: minimum 3 quotes for purchases above €10k. | Control design is incomplete without sole-source, emergency procurement and conflict-signoff procedures. | Control design | Respective owner | Open | Correct text, attach evidence, and reconcile across workbook.
Cross-chapter | 1.1, 1.3, 2.3 | Market/payment assumption inconsistency | Medium | 1.1 says DACH has safest payment habits "DSO < 60 days", but 1.2 working capital assumes 60-90 day DSO in export ramp-up. | These can differ by customer segment, but current text does not reconcile target DSO with modeled DSO. | Working capital realism | Respective owner | Open | Correct text, attach evidence, and reconcile across workbook.
Cross-chapter | 1.1, 1.4 | Capacity utilization endpoint ambiguity | Low | 1.1 says 100% project capacity by Year 5, while 1.4 stops at 95% in Y4. | Not an error, but the narrative should explicitly say Y5 reaches 100% after Y4 at 95%. | Narrative clarity | Respective owner | Open | Correct text, attach evidence, and reconcile across workbook.
Note on E4: Every issue in this sheet points to an exact trigger text or clause that should be corrected or evidenced.

## Evidence_Tracker
Evidence & Citation Tracker
Claims that should not remain in the plan without source support or hard backup
Chapter | Claim_or_Number | Evidence_Type_Required | Priority | Current_Status | Minimum_Backup_Needed | Owner | Comment
1.3 | 60-80% transformer equipment price increase since 2020 | Market source / industry report | High | Missing | Dated source with geography and product scope | Sales / Strategy | Load-bearing pricing claim
1.3 | 18-24 month lead times at leading OEMs | Industry source / supplier statements | High | Missing | Evidence with date and market scope | Sales / Strategy | Do not generalize without current basis
1.4 | Revenue / EBITDA / DSCR table 2026-2029 | Integrated model + assumption schedule | High | Partial | Excel model with assumptions and debt schedule | CFO | Numbers must trace
1.4 | 5-year payback | Valuation model | High | Missing | NPV/IRR/payback workbook with definitions | CFO | Need operating vs project timeline clarity
1.5 | Chapter 20 closure date and EU accession milestones | Official government/EU source | High | Missing | Official communiqué or chapter status record | CFO / Consultant | Current draft internally inconsistent
2.1 | Tourism share of GDP and manufacturing share of GDP | National statistics source | High | Missing | Single source with consistent definitions | CFO / Economist | Avoid wide unsupported ranges
2.2 | €584bn grid investment and €170bn smart-grid/digitalization figures | Official report / TYNDP / EC source | High | Missing | Document citation and date | Strategy Team | Critical demand thesis support
2.2 | 450 GW additional renewable capacity by 2028 | Official policy / market source | High | Missing | Source + scope | Strategy Team | Supports multi-decade demand argument
2.3 | 48-72h to N. Italy and 3-5 days to Austria/Germany | Logistics route test / freight quote | Medium | Missing | Lane-based routing evidence | Operations | Must align with chosen transport mode
3.1 | Flexible DOO structure with classes / convertible instruments | Legal memo | High | Missing | Article-level legal opinion under new law | Legal | Do not overstate legal flexibility
3.2 | Independent board / ESG committee architecture | Corporate resolutions / charters | Medium | Missing | Formal appointment and charters | Legal / Management | Concept vs implemented state
3.3 | ERP real-time integration benefits | Implementation roadmap / vendor proposal | Medium | Missing | Phased rollout and current-state limitations | IT / CFO | Avoid future-state wording as current state

## Controls_Check
Controls & Reconciliation Checks
Basic consistency checks across the harmonized workbook
Check | Formula_Cell_Input | Result | Interpretation
Funding total equals uses total (1.2) |  |  | Should be 0
1.4 revenue rows count |  |  | Should be 4
Critical issues count |  |  | Manual attention required
Task hard gates count |  |  | Tracks tasks that should block progression
Note on B4: Expected result is 0. Non-zero means sources and uses in chapter 1.2 are out of balance.