## 00_Navigation
MAREL ECOSYSTEM – CONTROL TOWER NAVIGATION
Navigation Index
Sheet | Purpose
00_Control | Governance, version, scope, canonical control owner
00_MAREL_Memory | Canonical memory map, module hierarchy, update status
01_Assumptions | Core assumptions and update frequencies
02_Permit_Master | Master register of permits and canonical IDs
03_Protocol_Tracker | Execution tracker, owners, next actions, escalations
04_Timeline_Model | Start/end dates, dependencies, control milestones
05_Cost_Model | Permit CAPEX structure and totals
13_CAPEX_Integration | Permit CAPEX phasing and controlled totals
14_Commissioning_Readiness | Gate-based readiness scoring for COD
06_Risk_Register | Risk scoring, mitigations, control owners
07_Project_Dashboard | Executive KPI dashboard
08_Error_Check | Integrity checks and traffic-light flags
09_Data_Validation | Controlled lists and lookup tables
10_Version_Log | Workbook revision history
11_Document_Control | Supporting documents and evidence pack
12_Update_Control | MAREL memory update protocol and review calendar

## 00_Control
Field | Value
Model_Name | ARS Industrial Permit Control Tower
Version | v5.0
Prepared_By
Reviewed_By
Date
Model_Type | MAREL-integrated project control workbook
Institutional_Standard | EBRD / Big4 / MAREL Canonical Control / CAPEX Integration
Confidentiality | Confidential
Canonical_Owner | ARS CFO / PMO Control Tower
Primary_Module | Permits / Regulatory / Commissioning Readiness
Update_Frequency | Weekly
Change_Control_Required | Yes
Control Notes
This workbook is aligned to MAREL central memory logic: one source of truth, controlled updates, explicit owners, version logging, and check-driven governance.

## 00_MAREL_Memory
Memory_Tag | Module | Submodule | Canonical_Record_ID | Source_Sheet | Owner | Update_Status | Last_Reviewed | Next_Review | Control_Priority | Comment
MAREL.PERMITS.001 | Permits | Urban / Regulatory | CAN-PER-001 | 02_Permit_Master | PMO / Legal | Active |  |  | High | Master permit universe
MAREL.PERMITS.002 | Permits | Protocol / Actions | CAN-PRO-001 | 03_Protocol_Tracker | PMO | Active |  |  | High | Execution follow-up layer
MAREL.PERMITS.003 | Permits | Timeline / Critical Path | CAN-TIM-001 | 04_Timeline_Model | PMO / Engineering | Active |  |  | High | Critical path alignment
MAREL.PERMITS.004 | Permits | Cost / CAPEX | CAN-CST-001 | 05_Cost_Model | Finance | Active |  |  | High | Permit CAPEX control
MAREL.PERMITS.005 | Permits | Risk | CAN-RSK-001 | 06_Risk_Register | Risk Manager | Active |  |  | Medium | Delay and compliance risk
MAREL.PERMITS.006 | Permits | Checks | CAN-CHK-001 | 08_Error_Check | QC / Audit | Active |  |  | High | Workbook integrity checks
MAREL.PERMITS.007 | Permits | Documents | CAN-DOC-001 | 11_Document_Control | Document Control | Active |  |  | Medium | Evidence pack register
MAREL.PERMITS.008 | Permits | Update Protocol | CAN-UPD-001 | 12_Update_Control | PMO / Finance | Active |  |  | High | Central memory refresh logic

## 01_Assumptions
Assumption_ID | Category | Description | Value | Unit | Source | Last_Update | Update_Frequency | Owner
ASM_001 | Timing | Permit contingency buffer | 20% | % | Internal governance |  | Quarterly | PMO
ASM_002 | Cost | Regulatory advisory contingency | 15% | % | Internal governance |  | Quarterly | Finance
ASM_003 | Cost | Base grid connection placeholder | 100000 | EUR | Internal placeholder |  | Monthly | Finance
ASM_004 | Timing | Default review cycle | 7 | days | Control policy |  | Weekly | PMO
ASM_005 | Risk | High risk threshold | 12 | score | Risk policy |  | Quarterly | Risk
ASM_006 | Cost | Base permit CAPEX contingency | 20% | % | Finance policy |  | Quarterly | Finance
ASM_007 | Timing | Critical path warning threshold | 14 | days | PMO rule |  | Weekly | PMO
ASM_008 | Readiness | Commissioning gate pass threshold | 85% | % | Control policy |  | Monthly | PMO
ASM_009 | Cost | Budget overrun warning threshold | 10% | % | Finance rule |  | Monthly | Finance

## 02_Permit_Master
Permit_ID | Canonical_Record_ID | Permit_Name | Authority | Phase | Duration_Days | Admin_Fees_EUR | Studies_Consultants_EUR | Utility_Connection_EUR | Total_Cost_EUR | Predecessor_ID | Risk_Level | Owner | Memory_Tag | Update_Status | Last_Reviewed | Source_Confidence | Notes
PER_001 | CAN-PER-UTU-001 | Urban-technical conditions | Municipality Tuzi – Urbanism | Development | 45 | 200 | 2000 | 0 |  |  | Medium | Legal / Urban Planner | MAREL.PERMITS.001 | Open |  | High | Initial gating permit
PER_002 | CAN-PER-EIA-002 | Environmental approval (EIA) | Environmental authority | Development | 90 | 1000 | 8000 | 0 |  | PER_001 | High | Environmental Consultant | MAREL.PERMITS.001 | Open |  | High | Public consultation possible
PER_003 | CAN-PER-CON-003 | Construction permit | Ministry / Municipality | Engineering | 75 | 5000 | 15000 | 0 |  | PER_002 | High | Project Architect | MAREL.PERMITS.001 | Open |  | Medium | Requires complete main project
PER_004 | CAN-PER-GRD-004 | Grid connection approval | CEDIS / DSO | Engineering | 120 | 1500 | 5000 | 100000 |  | PER_003 | High | Electrical Engineer | MAREL.PERMITS.001 | Open |  | High | Connection works may be required
PER_005 | CAN-PER-FIR-005 | Fire safety approval | Ministry of Interior / Fire Safety | Engineering | 45 | 1000 | 3000 | 0 |  | PER_003 | Medium | Fire Engineer | MAREL.PERMITS.001 | Open |  | High | Fire study required
PER_006 | CAN-PER-INS-006 | Technical inspection | Inspection commission | Commissioning | 30 | 2000 | 4000 | 0 |  | PER_004 | High | PMO / Technical | MAREL.PERMITS.001 | Open |  | Medium | Required before use permit
PER_007 | CAN-PER-USE-007 | Use permit / occupancy | Ministry / Municipality | Commissioning | 20 | 1500 | 2000 | 0 |  | PER_006 | High | Project Owner | MAREL.PERMITS.001 | Open |  | Medium | Final operating approval
Grand Total

## 03_Protocol_Tracker
Protocol_ID | Linked_Permit_ID | Responsible_Role | Status | Submission_Date | Expected_Approval_Date | Actual_Approval_Date | Days_Open | Next_Action_Date | Escalation_Level | Blocker | Comments | Memory_Tag | Update_Status | Overdue_Flag | Readiness_Weight
PROTO_001 | PER_001 | Legal / Urban planner | Not Started | [5 empty] | Level 1 |  | Submit request package | MAREL.PERMITS.002 | Pending |  | 1
PROTO_002 | PER_002 | Environmental consultant | Not Started | [5 empty] | Level 1 |  | Prepare EIA study | MAREL.PERMITS.002 | Pending |  | 1
PROTO_003 | PER_003 | Project architect | Not Started | [5 empty] | Level 2 |  | Compile main project | MAREL.PERMITS.002 | Pending |  | 1
PROTO_004 | PER_004 | Electrical engineer | Not Started | [5 empty] | Level 2 |  | Apply grid connection | MAREL.PERMITS.002 | Pending |  | 1
PROTO_005 | PER_005 | Fire engineer | Not Started | [5 empty] | Level 1 |  | Submit fire study | MAREL.PERMITS.002 | Pending |  | 1
PROTO_006 | PER_006 | Inspection commission | Not Started | [5 empty] | Level 2 |  | Plan inspection | MAREL.PERMITS.002 | Pending |  | 1
PROTO_007 | PER_007 | Project owner | Not Started | [5 empty] | Level 3 |  | Request use permit | MAREL.PERMITS.002 | Pending |  | 1
Formulas:
Days_Open = IF([Submission_Date]="","",TODAY()-[Submission_Date])
Overdue_Flag = IF(AND([Next_Action_Date]<TODAY(),[Status]<>"Approved",[Next_Action_Date]<>""),"YES","NO")

## 04_Timeline_Model
Permit_ID | Start_Date | Duration_Days | End_Date | Dependency | Critical_Path | Memory_Tag
MAREL.PERMITS.003
MAREL.PERMITS.003
MAREL.PERMITS.003
MAREL.PERMITS.003
MAREL.PERMITS.003
MAREL.PERMITS.003
MAREL.PERMITS.003

## 05_Cost_Model
Permit_ID | Phase | Admin_Fees_EUR | Studies_Consultants_EUR | Utility_Connection_EUR | Base_Total_EUR | Contingency_% | Contingency_EUR | Controlled_Total_EUR | Memory_Tag
MAREL.PERMITS.004
MAREL.PERMITS.004
MAREL.PERMITS.004
MAREL.PERMITS.004
MAREL.PERMITS.004
MAREL.PERMITS.004
MAREL.PERMITS.004
Grand Total

## 13_CAPEX_Integration
Module | Source | 2026_EUR | 2027_EUR | 2028_EUR | 2029_EUR | Total_EUR | Control_Note
Permit Admin Fees | 05_Cost_Model | [5 empty] | Linked from permit cost model
Studies & Consultants | 05_Cost_Model | [5 empty] | Linked from permit cost model
Utility Connection | 05_Cost_Model | 0 |  |  |  |  | Linked from permit cost model
Contingency | 05_Cost_Model | [5 empty] | Linked from permit cost model
Controlled Permit Total | 05_Cost_Model | [5 empty] | Total permit CAPEX under governance

## 14_Commissioning_Readiness
Gate_ID | Requirement | Linked_Permit_ID | Status | Weight | Score | Comment
GATE_001 | Urban-technical conditions approved | PER_001 | Not Started | 10% |  | Foundational permit
GATE_002 | Environmental approval obtained | PER_002 | Not Started | 15% |  | EIA / environmental clearance
GATE_003 | Construction permit obtained | PER_003 | Not Started | 20% |  | Construction go-live
GATE_004 | Grid connection secured | PER_004 | Not Started | 20% |  | Power availability
GATE_005 | Fire approval secured | PER_005 | Not Started | 10% |  | Safety gate
GATE_006 | Technical inspection passed | PER_006 | Not Started | 15% |  | Pre-use inspection
GATE_007 | Use permit obtained | PER_007 | Not Started | 10% |  | Commercial operation gate
Readiness Index
Threshold
Pass / Fail

## 06_Risk_Register
Risk_ID | Category | Description | Probability | Impact | Risk_Score | Mitigation_Action | Owner | Status | Linked_Permit_ID | Memory_Tag | Risk_Band
RSK_001 | Schedule | UTU or planning delay | 40% | 3 |  | Front-load application pack | PMO | Open | PER_001 | MAREL.PERMITS.005
RSK_002 | Environmental | EIA review extension | 50% | 4 |  | Early consultant engagement | Environmental | Open | PER_002 | MAREL.PERMITS.005
RSK_003 | Regulatory | Construction permit rework | 30% | 4 |  | Revise design package | Architect | Open | PER_003 | MAREL.PERMITS.005
RSK_004 | Infrastructure | Grid reinforcement delay | 60% | 5 |  | Coordinate with DSO early | Electrical | Open | PER_004 | MAREL.PERMITS.005

## 07_Project_Dashboard
PROJECT CONTROL DASHBOARD – MAREL HARMONIZED
Permit Progress | Permit CAPEX | Readiness & Control
Total Permits | Base Permit CAPEX | Readiness Index
Open / Pending | Contingency | Threshold
Approved | Controlled Total | Pass / Fail
High Risk Items | Missing Checks | Overdue Actions
Missing Documents

## 08_Error_Check
Check_ID | Description | Result | Flag | Severity | Memory_Tag
CHK_001 | Duplicate Permit IDs |  |  | Critical | MAREL.PERMITS.006
CHK_002 | Protocol without Permit |  |  | Critical | MAREL.PERMITS.006
CHK_003 | Missing Authority |  |  | Medium | MAREL.PERMITS.006
CHK_004 | Negative Cost Inputs |  |  | Critical | MAREL.PERMITS.006
CHK_005 | Missing Duration |  |  | Medium | MAREL.PERMITS.006
CHK_006 | Protocol IDs Missing |  |  | Low | MAREL.PERMITS.006
CHK_007 | Permit Without Owner |  |  | Medium | MAREL.PERMITS.006
CHK_008 | Overdue protocol actions |  |  | Critical | MAREL.PERMITS.006
CHK_009 | Missing supporting documents |  |  | Medium | MAREL.PERMITS.006
CHK_010 | High risks open |  |  | Medium | MAREL.PERMITS.006
CHK_011 | Readiness below threshold |  |  | Critical | MAREL.PERMITS.006

## 09_Data_Validation
Status_List | Risk_Status_List | Update_Status_List | Gate_Status_List
Not Started | Open | Pending | Not Started
In Preparation | Monitoring | Updated | In Progress
Submitted | Mitigated | Validated | Approved
Under Review | Closed | Archived | Failed
Approved |  |  | Waived
Rejected
Delayed

## 10_Version_Log
Version | Date | Change_Summary | Prepared_By | Reviewed_By | Approval_Status
v3.0 |  | Base control tower workbook |  |  | Superseded
v5.0 |  | MAREL memory harmonization, CAPEX integration, commissioning readiness, expanded controls |  |  | Draft

## 11_Document_Control
Doc_ID | Linked_Permit_ID | Document_Name | Owner | Revision | Status | Folder_Path | Evidence_Type | Last_Updated | Memory_Tag
DOC_001 | PER_001 | Land ownership package | Legal | A | Missing |  | Legal |  | MAREL.PERMITS.007
DOC_002 | PER_002 | Environmental baseline / EIA study | Environmental | A | Pending |  | Technical |  | MAREL.PERMITS.007
DOC_003 | PER_003 | Main project and revisions | Architect | A | Pending |  | Technical |  | MAREL.PERMITS.007

## 12_Update_Control
Update_ID | Module | Source_Sheet | Control_Owner | Update_Frequency | Last_Update | Next_Update | Validation_Check | Escalation_Rule | Status | Comment
UPD_001 | Permit Master | 02_Permit_Master | PMO / Legal | Weekly |  |  | 08_Error_Check | Escalate after 7 days overdue | Active | Canonical source refresh
UPD_002 | Protocol Tracker | 03_Protocol_Tracker | PMO | Weekly |  |  | 08_Error_Check | Escalate after missed action date | Active | Execution meeting update
UPD_003 | Timeline | 04_Timeline_Model | PMO / Engineering | Weekly |  |  | 08_Error_Check | Escalate if critical path slips | Active | Schedule refresh
UPD_004 | Cost Model | 05_Cost_Model | Finance | Monthly |  |  | 08_Error_Check | Escalate on budget overrun | Active | Budget refresh
UPD_005 | Document Control | 11_Document_Control | Document Control | Weekly |  |  | 08_Error_Check | Escalate missing evidence | Active | Evidence pack refresh